## Epic Overview
E20 – Resilience & Tier-0 Operations (SRE)
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E20
Epic name | Resilience & Tier-0 Operations (SRE)
Goal | Operate the WellnessZ production service as a Tier-0 system at 99.99 % availability inside a single jurisdiction: a two-region in-country deployment with automated failover, service-level objectives and error budgets per critical journey, production-volume performance evidence, chaos and disaster-recovery drills, zero-downtime change and an on-call operating model with runbooks and post-incident learning.
Business value | Closes the largest operational risks in the GRC register (G9 service unavailability, R8 single region, R9 audit throughput ceiling, R36 pipeline never run against a real cloud). Fitness-for-duty status reaches rostering even during a regional outage, so safety-critical rostering never works from stale data for long. 99.99 % allows about 52 minutes of downtime a year – this only holds if failover is automated and rehearsed.
In scope | • Two-region in-country Azure deployment (primary + warm standby), allowed-locations policy, DNS-only traffic failover • SLOs, error budgets and multi-window burn-rate alerts as code for the critical journeys • Production-volume load, soak and capacity tests; capacity model per environment • Chaos experiments and quarterly DR drills (zone, region, database, broker, identity provider, ransomware restore) • Zero-downtime migrations (expand / contract), progressive delivery, feature-flag dark launches • Observability: golden signals, synthetic probes per region, on-call, runbooks, post-incident reviews; BCP manual fallback
Out of scope | • Enterprise SOC / SIEM operation (E19 and client SOC) • Commercial hosting decisions already taken in the Tier-0 decision pack • Business continuity of non-IT processes beyond the OH manual fallback
Primary stakeholders / roles | CIO; Head of SRE / Platform; Platform & SRE team; DBA; Network; Crew scheduling (consumer of fitness status); CMO (BCP fallback); Cyber GRC; Release manager
Success KPIs | • Availability of PROD (measured SLO) ≥ 99.99 % per calendar month • Region failover proven every quarter: RTO ≤ 15 min, RPO ≤ 5 min (Tier-0 decision pack targets) • Quarterly isolated restore test pass rate 100 % • p95 API latency ≤ 400 ms at 1.5 × forecast peak; 0 SLO breaches caused by capacity • Change failure rate ≤ 10 %; mean time to restore (P1) ≤ 30 min • 0 schema migrations that require downtime
Dependencies | E15 Integration (broker adapter D3, rostering transport); E16 Identity & security (customer-managed keys, envelope encryption); E19 Security (SEC-E03 admission, SEC-E04 private control plane, SEC-E09 CMK); decision D1 / D9 and the Tier-0 cost decision pack
Standards & references | • SOC2 A1.2 / A1.3 availability and recovery • ISO22301 business continuity; ISO27001 A.5.30, A.8.13, A.8.14 • SRE: service-level objectives, error budgets, multi-window burn-rate alerting • CIS-K8S benchmarks for AKS
Evidence base (why now) | Architecture doc §12: 'Region failure – not automated in the current IaC (single region)'; release notes 3–5: bulk invitation, 50K-staff vaccination campaign, tracing over large rosters, worklists and exports not load-tested at production volume; R9 audit advisory lock throughput ceiling 'to be load-tested'; R36 promotion pipeline not yet executed against real clouds.
Recommended start horizon | H1 – Go-live readiness (months 0–6) for two-region, SLOs, load tests and the first DR drill; H2 for chaos automation and progressive delivery
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E20 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E20-HLR-01 | The production service shall run in two regions of the same jurisdiction (primary and warm standby) with an asynchronous database replica, customer-managed keys, immutable backups replicated only in-country and DNS-only traffic failover; an allowed-locations policy shall block any resource outside the jurisdiction. | Single-jurisdiction residency and Tier-0 availability are client constraints; one region delivers about 99.91 % by composite SLA. | Must | SOC2 A1.2; ISO22301; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E20-HLR-02 | Each critical journey (sign-in, triage queue, fitness status to rostering, urgent mental-health call-back, contact tracing, partner referral) shall have a published SLO, an error budget and burn-rate alerts managed as code. | Alerting on symptoms users feel instead of host metrics; error budget governs release pace. | Must | SRE; SOC2 CC7.2 | ALL – All subsidiaries & departments (group-wide)
E20-HLR-03 | The platform shall be load-, soak- and stress-tested at production volume before go-live and before each major release, including a 50K-staff vaccination campaign, bulk invitations, roster-wide contact tracing, worklists, roll-ups, exports and audit-chain write throughput. | Release notes 3–5 state that none of these was tested at production volume. | Must | SOC2 A1.1; ISO27001 A.8.6 | ALL – All subsidiaries & departments (group-wide)
E20-HLR-04 | Resilience shall be verified by scheduled chaos experiments and quarterly disaster-recovery drills covering zone, region, database, broker and identity-provider failure, plus a restore from immutable backup into an isolated environment. | Recovery targets are only credible when rehearsed; evidence is required for SOC 2 availability criteria. | Must | ISO22301; SOC2 A1.3 | ALL – All subsidiaries & departments (group-wide)
E20-HLR-05 | Releases shall not require downtime: database migrations shall follow expand / contract, application releases shall be progressive (canary or blue / green) with automatic rollback, and new features shall be dark-launched behind governed feature flags. | Tier-0 budget leaves no room for maintenance windows; flags exist today as plumbing only. | Should | SOC2 CC8.1; ISO27001 A.8.32 | ALL – All subsidiaries & departments (group-wide)
E20-HLR-06 | Operations shall have 24×7 on-call with runbooks for every alert, synthetic probes per region, post-incident reviews without blame, and a documented manual fallback for fitness-for-duty decisions during an outage. | Architecture doc §12: BCP must define the manual fallback for fitness decisions. | Must | ISO22301; IOSA; SOC2 CC7.4 | FLT – Flight Operations; CAB – Cabin Services; ALL – All subsidiaries & departments (group-wide)

## Feature List
E20 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E20-F01 | Two-region in-country topology | Recovery stack in the paired in-country region: warm AKS cluster, async PostgreSQL replica with CMK, replicated registry, immutable backup vault, Traffic Manager DNS failover, allowed-locations policy. | SRE; DBA; Network | Must | E20-HLR-01 | Policy denies out-of-country resources; replica lag alert ≤ 5 min; failover runbook automated end to end in UAT. | Same design for a UK or UAE region pair; UAE Central needs an access request.
E20-F02 | SLOs, error budgets and burn-rate alerting | SLO catalogue per journey, recording rules and burn-rate alerts as code, error-budget policy that pauses feature releases when exhausted. | SRE; Product owners | Must | E20-HLR-02 | Six journeys with SLOs live; alert fires in a fault-injection test; monthly SLO report to the CIO. | Fitness-status journey owned jointly with crew scheduling.
E20-F03 | Performance and capacity engineering | Load-test suite with production-shaped synthetic data, soak tests, capacity model and per-release performance budget in the pipeline. | SRE; QA; Core API team | Must | E20-HLR-03 | Campaign, tracing, worklist and audit scenarios pass at 1.5 × forecast peak; capacity model approved. | Synthetic data only – never production health data.
E20-F04 | Chaos and disaster-recovery programme | Chaos experiments in UAT on a schedule, quarterly region failover and restore drills in PROD-like conditions, ransomware recovery from immutable copies. | SRE; DBA; Cyber GRC | Must | E20-HLR-04 | Drill report each quarter with measured RTO / RPO; findings tracked to closure. | First drill is a go-live condition.
E20-F05 | Zero-downtime delivery | Expand / contract migration guideline and lint, canary releases with automatic analysis and rollback, governed feature flags (owner, expiry, audit). | Platform; Core API team; Release manager | Should | E20-HLR-05 | Two consecutive releases with zero downtime; every flag has owner and expiry. | Flags must never switch off a safety control.
E20-F06 | On-call, runbooks and operational learning | On-call rota, runbook per alert, synthetic probes per region, post-incident review template, BCP manual fallback for fitness decisions. | SRE; CMO; Crew scheduling | Must | E20-HLR-06 | 100 % of paging alerts link a runbook; BCP fallback exercised in a tabletop with crew scheduling. | Manual fallback covers crew and safety-sensitive ground roles.

## Implementation Backlog
E20 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E20-BL-001 | E20-F01 |  | Enabler | Retarget all environments to the in-country region pair and add an allowed-locations policy to the Terraform landing zone | No resource outside the jurisdiction in policy compliance report; plan applies cleanly in DEV | 8 | H1 | P1 | SRE / Platform | E19 |  | Not started
E20-BL-002 | E20-F01 |  | Enabler | Build the recovery-region stack: warm AKS cluster, async PostgreSQL replica with customer-managed key, replicated registry, immutable backup vault | Replica lag < 5 min under load; vault deletion lock and dual control verified | 13 | H1 | P1 | SRE / Platform | E16, E19 |  | Not started
E20-BL-003 | E20-F01 |  | Story | As the on-call engineer I want a one-command, scripted region failover (promote replica, scale cluster, switch DNS, verify) so that RTO ≤ 15 min is achievable at 3 a.m. | Automated runbook executes in UAT within 15 min; outbox replay re-sends fitness status after failover | 13 | H1 | P1 | SRE / Platform | E15 |  | Not started
E20-BL-004 | E20-F02 |  | Enabler | Define SLOs and error budgets for six critical journeys and implement burn-rate alerts (1 h / 6 h windows) as code | SLO catalogue approved by product owners; alerts tested by fault injection | 8 | H1 | P1 | SRE / Platform | – |  | Not started
E20-BL-005 | E20-F02 |  | Task | Agree the error-budget policy (release freeze, escalation) with the CIO and product owners | Signed policy; first monthly SLO report delivered | 2 | H1 | P2 | Product Owner; SRE | – |  | Not started
E20-BL-006 | E20-F03 |  | Enabler | Build a load-test suite with production-shaped synthetic data for 50K staff, 30K crew rosters and five years of case history | Generator reproducible; no real data; scenarios scripted for campaign, tracing, worklists, exports | 13 | H1 | P1 | QA; SRE / Platform | – |  | Not started
E20-BL-007 | E20-F03 |  | Story | As the CIO I want evidence that the platform sustains 1.5 × forecast peak so that go-live does not depend on assumptions | Report with p95 / p99 latency, error rate, DB saturation and audit-chain throughput; defects fixed or accepted | 8 | H1 | P1 | SRE / Platform | – |  | Not started
E20-BL-008 | E20-F03 |  | Spike | Assess the audit-chain advisory lock (R9) under load and decide whether partitioned chains are needed | Measured writes per second vs forecast; decision record | 3 | H1 | P2 | Platform / Backend | E16 |  | Not started
E20-BL-009 | E20-F04 |  | Enabler | Introduce chaos experiments in UAT (pod, node, zone, database failover, broker outage, IdP outage) on a monthly schedule | Experiments run unattended; steady-state hypothesis checked; results published | 8 | H2 | P2 | SRE / Platform | E15 |  | Not started
E20-BL-010 | E20-F04 |  | Task | Run the first region failover and isolated restore drill before PROD go-live | Measured RTO ≤ 15 min, RPO ≤ 5 min; drill report signed by the CIO and Cyber GRC | 5 | H1 | P1 | SRE / Platform; Cyber GRC | E19 |  | Not started
E20-BL-011 | E20-F05 |  | Enabler | Expand / contract migration guideline with a Flyway lint in CI that blocks destructive changes in a single release | Lint rejects DROP / RENAME without contract phase; guideline in developer guide | 5 | H2 | P2 | Platform / Backend | – |  | Not started
E20-BL-012 | E20-F05 |  | Enabler | Canary releases with automated analysis against SLOs and automatic rollback in the promotion pipeline | Canary of 10 % for 30 min; rollback on SLO breach proven in UAT | 8 | H2 | P2 | SRE / Platform | – |  | Not started
E20-BL-013 | E20-F05 |  | Story | As a release manager I want feature flags with owner, expiry and audit so that dark launches do not become permanent configuration | Flag register; expired flags fail the build; flag change audited | 5 | H2 | P3 | Platform / Backend | E18 |  | Not started
E20-BL-014 | E20-F06 |  | Task | Set up 24×7 on-call, runbook per paging alert, synthetic probes per region and the post-incident review process | Rota staffed; probes from both regions; first review published | 5 | H1 | P1 | SRE / Platform | – |  | Not started
E20-BL-015 | E20-F06 |  | Task | Document and exercise the manual fallback for fitness-for-duty decisions with crew scheduling and the CMO | Tabletop completed; fallback form and contact tree approved | 3 | H1 | P1 | Clinical SME (OH Nurse / Physician); Crew scheduling | E05 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty