## Epic Overview
E21 – Accessibility & Internationalisation
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E21
Epic name | Accessibility & Internationalisation
Goal | Make every WellnessZ front end and generated document usable by every employee, crew member, clinician and partner: WCAG 2.2 AA conformance across the four web apps and the mobile app, full Arabic right-to-left support, the workforce's main languages for employee-facing content, locale-aware formats for a multinational crew, and governed translation of clinical content.
Business value | A 50K multinational workforce, including outstation and night-shift staff, can only use self-service if it is accessible and in their language; inaccessible health services expose the group to discrimination claims and erode trust in the confidential pathways. Localised clinical content (e.g. validated screening translations) is a clinical-safety issue, not a cosmetic one.
In scope | • WCAG 2.2 AA audit and remediation of the OH workspace, employee app, manager workspace and partner portal • Accessibility in the SDLC: automated checks in CI, manual audit, assistive-technology testing • Arabic RTL across all four apps; Arabic shaping and bidirectional text in generated PDFs • Multilingual employee content (top workforce languages from HRIS data) with translation management • Locale formats: dates, numerals, time zones of stations, optional Hijri display • Clinical translation governance (validated instrument translations, back-translation, sign-off)
Out of scope | • Translation of the clinical record itself (records stay in the clinician's language) • Sign-language interpretation services (procured by OH)
Primary stakeholders / roles | Head of Experience; UX / accessibility lead; Nursing Head; CMO; DPO (content-free notifications in every language); HR diversity & inclusion; employee representatives
Success KPIs | • 0 open WCAG 2.2 AA critical or serious issues across the four web apps and the mobile app • 100 % of employee-facing screens and documents available in Arabic with correct RTL • ≥ 95 % of employee-facing content in the top five workforce languages • Task-completion rate parity (± 5 points) between languages in usability tests • Approved clinical translations published within 10 working days of source approval
Dependencies | E13 Portal / app; E18 Master data (languages, templates); E22 Native mobile (platform accessibility APIs); E03 / E09 content owners for clinical translations
Standards & references | • WCAG22: W3C WCAG 2.2 level AA • EN301549: EN 301 549 accessibility requirements for ICT • PDF-UA: ISO 14289 accessible PDF • Unicode bidirectional algorithm (UAX #9); CLDR locale data • ISPOR good practice for translation of patient-reported outcome measures
Evidence base (why now) | Employee app already switches Arabic to dir="rtl" on the portal screens and holds en / ar / fr strings for self-referral; the OH workspace, manager workspace and partner portal have no locale layer; increment-2 sign-off S14: clinical-text guard vocabulary is English only; triage advice texts en / ar / fr are drafts; no WCAG audit is recorded in the delivery evidence.
Recommended start horizon | H1 – audit and Arabic for employee-facing journeys before go-live; H2 – workspaces, further languages and PDFs
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E21 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E21-HLR-01 | All four web apps and the mobile app shall conform to WCAG 2.2 level AA, verified by an independent manual audit and by automated checks on every build. | Legal accessibility duties and inclusion; the employee app is the main entry to confidential pathways. | Must | WCAG22; EN301549 | ALL – All subsidiaries & departments (group-wide)
E21-HLR-02 | Every front end and every employee-facing generated document shall support Arabic with correct right-to-left layout, Arabic glyph shaping and mixed-direction text. | Arabic is a primary language for the workforce in the Gulf operations; only part of the employee app supports it today. | Must | WCAG22; PDF-UA | ALL – All subsidiaries & departments (group-wide)
E21-HLR-03 | Employee-facing content shall be available in the workforce's main languages, chosen from HRIS language data, with a translation-management workflow and fall-back to English. | Multinational crews and ground staff; low-literacy and second-language users at airside posts. | Should | LOCAL-PDP; WCAG22 | ALL – All subsidiaries & departments (group-wide)
E21-HLR-04 | Clinical content shown to employees in another language (screening instruments, advice, signposting, consent texts) shall use validated or back-translated versions approved by the content owner before release. | A wrong translation of a PHQ-9 item or a consent text is a clinical and legal risk. | Must | ISO45003; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E21-HLR-05 | Dates, times, numbers and calendars shall follow the user's locale, and crew-facing times shall show the station time zone alongside UTC. | Crew operate across time zones; misread times cause missed appointments and protocol timers. | Should | ICAO-A6 | FLT – Flight Operations; CAB – Cabin Services

## Feature List
E21 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E21-F01 | Accessibility audit and remediation | Independent WCAG 2.2 AA audit of all apps; remediation backlog; accessibility statement per app. | UX / accessibility lead; Web team | Must | E21-HLR-01 | Audit report; 0 critical / serious issues open; statements published. | Kiosk check-in and queue board included.
E21-F02 | Accessibility in the SDLC | Automated accessibility checks in CI for every app, component library with accessible primitives, assistive-technology test protocol. | Web team; QA | Must | E21-HLR-01 | Build fails on new serious violations; screen-reader test protocol run each release. | None
E21-F03 | Arabic and RTL across apps and documents | Locale layer in the three workspaces, RTL layout, Arabic fonts and shaping in PDF generation, bidirectional text tests. | Web team; Platform / Backend | Must | E21-HLR-02 | All screens pass RTL visual review; Arabic PDFs render correctly and are tagged. | Partner portal Arabic optional per partner.
E21-F04 | Multilingual content management | Translation keys externalised, translation-management workflow, language selection from HRIS preference, English fall-back. | Frontend / UX; Content owners | Should | E21-HLR-03 | Top-five languages live on employee journeys; missing keys reported, never blank. | Content-free notifications checked in every language.
E21-F05 | Clinical translation governance | Register of translated clinical content with source version, method (validated / back-translated), approver and licence. | CMO; Nursing Head; Mental-health lead | Must | E21-HLR-04 | No clinical text published in a language without an approved translation record. | Licensed instrument translations may carry fees.
E21-F06 | Locale and time-zone handling | Locale-aware formatting; station time zone plus UTC for crew; optional Hijri display. | Frontend / UX | Should | E21-HLR-05 | Appointment and protocol times shown correctly across 5 time-zone test cases. | Station list from E18 master data.

## Implementation Backlog
E21 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E21-BL-001 | E21-F01 |  | Task | Commission an independent WCAG 2.2 AA audit of the four web apps and the mobile build | Audit report with issue list by severity and success criterion | 3 | H1 | P1 | Product Owner; UX / accessibility lead | – |  | Not started
E21-BL-002 | E21-F01 |  | Story | As an employee using a screen reader I want to complete self-referral, booking and consent screens so that I can use confidential services independently | Journeys pass manual screen-reader tests (desktop and mobile); no critical issue open | 13 | H1 | P1 | Frontend / UX | E13 |  | Not started
E21-BL-003 | E21-F01 |  | Story | As a clinician with low vision I want the OH workspace worklists and forms to meet contrast, focus and target-size criteria | Worklists and forms pass WCAG 2.2 AA (incl. 2.4.11 focus not obscured, 2.5.8 target size) | 13 | H2 | P2 | Frontend / UX | – |  | Not started
E21-BL-004 | E21-F02 |  | Enabler | Add automated accessibility checks to the web unit and end-to-end tests of all four apps | CI fails on new serious violations; baseline recorded | 5 | H1 | P1 | Frontend / UX; QA | – |  | Not started
E21-BL-005 | E21-F03 |  | Enabler | Introduce a shared locale layer (language, direction, formatting) in the OH workspace, manager workspace and partner portal | Language switch works without reload; RTL mirrored layout; tests in en and ar | 8 | H2 | P2 | Frontend / UX | E18 |  | Not started
E21-BL-006 | E21-F03 |  | Enabler | Arabic glyph shaping, bidirectional text and embedded fonts in PDF generation; tagged PDF output | Certificates, letters and results render Arabic correctly; PDF/UA checker passes | 8 | H1 | P1 | Platform / Backend | – |  | Not started
E21-BL-007 | E21-F03 |  | Story | As an Arabic-speaking employee I want every employee-app screen in Arabic so that I understand my fitness outcome and my rights | 100 % employee-app screens translated and RTL-reviewed | 8 | H1 | P1 | Frontend / UX | E13 |  | Not started
E21-BL-008 | E21-F04 |  | Enabler | Externalise all UI strings and connect a translation-management workflow (export, translate, review, import) | No hard-coded strings in employee journeys; missing-key report in CI | 5 | H2 | P2 | Frontend / UX | – |  | Not started
E21-BL-009 | E21-F04 |  | Story | As a crew member I want the app in my preferred language from HRIS so that I do not have to set it on every device | Preference read from HRIS / profile; fall-back to English; change audited | 3 | H2 | P2 | Frontend / UX | E15 |  | Not started
E21-BL-010 | E21-F05 |  | Task | Create the clinical translation register and approve validated translations of PHQ-9, GAD-7, consent and signposting texts | Register in E18; each translation has source version, method, approver and licence | 5 | H1 | P1 | Clinical SME (OH Nurse / Physician); DPO | E09, E18 |  | Not started
E21-BL-011 | E21-F05 |  | Task | Extend the clinical-text guard vocabulary to Arabic and French (increment-2 sign-off S14) | Vocabulary approved by DPO and Nursing Head; guard tests in three languages | 3 | H1 | P1 | Security & Privacy; Clinical SME (OH Nurse / Physician) | E16 |  | Not started
E21-BL-012 | E21-F06 |  | Story | As a crew member I want appointment and protocol times in my station time zone and UTC so that I never miss a PEP or surveillance appointment on a layover | Times rendered with station zone and UTC; tested across 5 zones | 5 | H2 | P2 | Frontend / UX | E18 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty