## Epic Overview
E22 – Native Mobile, Offline & Field Capability
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E22
Epic name | Native Mobile, Offline & Field Capability
Goal | Turn the Capacitor shell into a production crew and field app: secure on-device storage and app-protection policies, offline-tolerant capture at airside first-aid posts and for telephone triage with an encrypted queue and safe sync, NFC badge scan, content-free push notifications with per-user channel preferences, and crew features that work on layover.
Business value | Most OH demand comes from a dispersed 24×7 workforce: ramp, cargo, catering, engineering and crew away from base. A first-aid post that cannot register an encounter when the network drops loses the case and the evidence. Push and a status wallet (medical certificate, travel vaccinations) reduce lapses and missed appointments.
In scope | • Secure storage (Keychain / Keystore) and app-protection SDK (MAM) – store and MDM release • Offline capture for first-aid posts and telephone triage: minimal dataset, encrypted local queue, sync and conflict handling • NFC / badge scan against an HRIS cache for registration under 60 s • Push notifications (content-free) and per-user channel preferences • Crew features: status wallet (certificate validity, travel vaccinations), roster-aware reminders, layover access • Device test matrix, crash reporting without PHI, release engineering
Out of scope | • Offline access to the full clinical record (deliberately not cached) • Bring-your-own-device policy (client IT) • Mobile hardening assessment itself (E19 SEC-E11)
Primary stakeholders / roles | Head of Experience; Mobile team; First aiders; Clinic reception; OH nurses on telephone triage; Crew; Client mobility / MDM team; DPO; CISO
Success KPIs | • First-aid encounter registered in < 60 s, including with no network (E01-HLR-03) • 0 health data at rest unprotected on devices (MASVS L2 assessment pass) • Sync conflict rate < 0.5 %; 0 lost offline encounters • Crash-free sessions ≥ 99.5 % • App adoption ≥ 70 % of crew within 12 months of release • Push delivered within 1 minute for ≥ 95 % of messages
Dependencies | E13 Portal / app; E15 Integration (HRIS cache, push provider); E16 Identity (token storage, MFA); E19 Security (SEC-E11 MASVS); decision D4 mobile distribution
Standards & references | • OWASP-MASVS v2 (L2 for PHI apps) • LOCAL-PDP; ISO27001 A.8.1 user end-point devices • Platform app-store health-data guidelines • WCAG22 for mobile
Evidence base (why now) | Risk R6 / G14: refresh token in memory only until the secure-storage plug-in is registered, MAM SDK not integrated; increment-1 limitations: no native NFC, offline retry in memory only, telephone triage not offline-capable, SMS / push are logging adapters, no per-user channel opt-in; client requirement E01-HLR-03: airside posts work offline-tolerant (mobile sync).
Recommended start horizon | H1 – secure storage, MAM and store / MDM release before crew go-live; H2 – offline capture, NFC, push and wallet
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E22 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E22-HLR-01 | The mobile app shall store tokens only in hardware-backed secure storage, enforce app-protection policies (no copy / paste or backup of app data, PIN, remote wipe) and be distributed through MDM for managed devices. | Risk R6 and G14; decision D4 recommends MDM-managed distribution with app protection. | Must | OWASP-MASVS; ISO27001 | FLT – Flight Operations; CAB – Cabin Services; GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E22-HLR-02 | First-aid posts and telephone triage shall continue to capture a minimal encounter dataset without network, held in an encrypted local queue and synchronised idempotently when connectivity returns. | Airside and night-shift posts lose connectivity; E01-HLR-03 requires offline tolerance. | Must | LOCAL-PDP; ISO45001 | GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E22-HLR-03 | Registration shall accept NFC / badge scan against a cached HRIS lookup so that a walk-in is registered in under 60 seconds. | Speed at the point of injury; current flow is manual. | Should | ISO45001 | GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E22-HLR-04 | The app shall deliver content-free push notifications and let each user choose channels (push, SMS, e-mail) within the limits of mandatory safety messages. | Push and SMS are logging adapters today; no per-user opt-in. | Should | LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E22-HLR-05 | Crew shall see a status wallet (medical certificate validity, travel vaccinations, upcoming surveillance) and roster-aware reminders, usable on layover. | Certificate lapses ground crew; KPI 'crew medical certificate lapses = 0'. | Should | EASA-MED; ICAO-A1 | FLT – Flight Operations; CAB – Cabin Services

## Feature List
E22 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E22-F01 | Secure, managed mobile platform | Secure-storage plug-in, MAM SDK, jailbreak / root signals, MDM managed configuration, store and enterprise distribution pipeline. | Mobile team; Client MDM team | Must | E22-HLR-01 | Tokens in Keychain / Keystore; MAM policies enforced in test; signed builds distributed through MDM. | Unmanaged devices limited to web portal if policy requires.
E22-F02 | Offline encounter capture and sync | Minimal dataset form, encrypted queue with device-bound key, idempotent sync with Idempotency-Key, conflict rules, max offline age, wipe on sign-out. | First aider; Clinic reception; OH nurse | Must | E22-HLR-02 | Encounters created offline appear once after sync; queue unreadable without app unlock; 72 h maximum offline age. | Only first-aid and triage data offline – no record browsing.
E22-F03 | NFC and badge registration | NFC / barcode badge scan, HRIS lookup cache with short TTL and minimal fields. | First aider; Clinic reception | Should | E22-HLR-03 | Registration < 60 s in field test at three posts. | Badge technology varies by station.
E22-F04 | Push and channel preferences | Push provider integration through the notification gateway, content-free templates, per-user channel preferences, mandatory-message rules. | Employee; Crew; DPO | Should | E22-HLR-04 | Push delivered < 1 min for 95 %; no clinical words in any push (content rule tests). | Mandatory safety advisories cannot be switched off.
E22-F05 | Crew status wallet and reminders | Wallet card showing statuses only, offline-readable, roster-aware reminders. | Crew; AME; Crew licensing | Should | E22-HLR-05 | Wallet shows status without diagnosis; reminders before expiry at 60 / 30 / 7 days. | Status only – no clinical detail on the device.

## Implementation Backlog
E22 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E22-BL-001 | E22-F01 |  | Enabler | Register the secure-storage plug-in for refresh tokens on iOS and Android and remove in-memory fall-back in release builds | Tokens persisted only in Keychain / Keystore; MASVS storage checks pass | 5 | H1 | P1 | Mobile | E19 |  | Not started
E22-BL-002 | E22-F01 |  | Enabler | Integrate the app-protection (MAM) SDK and managed configuration; verify selective wipe | Copy / paste and backup blocked; selective wipe removes app data in test | 8 | H1 | P1 | Mobile | E19 |  | Not started
E22-BL-003 | E22-F01 |  | Task | Set up enterprise / MDM distribution and store listings with health-data declarations | Signed builds delivered through MDM to pilot group; store review passed | 5 | H1 | P1 | Mobile; Product Owner | – |  | Not started
E22-BL-004 | E22-F02 |  | Story | As a first aider at an airside post I want to register an injury when the network is down so that no encounter is lost | Offline form with minimal dataset; encrypted queue; sync once online; duplicate-safe | 13 | H2 | P1 | Mobile; Platform / Backend | E01 |  | Not started
E22-BL-005 | E22-F02 |  | Enabler | Idempotent sync API with conflict rules and maximum offline age for queued encounters | Server rejects stale (> 72 h) items for manual review; replay is idempotent | 8 | H2 | P1 | Platform / Backend | E15 |  | Not started
E22-BL-006 | E22-F02 |  | Story | As a triage nurse on night shift I want telephone triage to continue offline with the protocol script cached so that outstations get the same quality | Approved protocol versions cached; result synced with protocol version id | 8 | H2 | P2 | Mobile; Clinical SME (OH Nurse / Physician) | E02 |  | Not started
E22-BL-007 | E22-F03 |  | Story | As clinic reception I want to scan a staff badge by NFC so that the walk-in is registered in under 60 seconds | NFC and barcode supported; HRIS cache TTL ≤ 24 h; field test at three posts | 5 | H2 | P2 | Mobile | E15 |  | Not started
E22-BL-008 | E22-F04 |  | Enabler | Push channel adapter behind NotificationChannel with content-free templates | Adapter selected by @Order; content rules tested; delivery metrics | 5 | H2 | P2 | Platform / Backend | E15 |  | Not started
E22-BL-009 | E22-F04 |  | Story | As an employee I want to choose how I am contacted (push, SMS, e-mail) so that reminders reach me without exposing my health | Preference per user; mandatory messages flagged; audit of changes | 5 | H2 | P2 | Frontend / UX | E16 |  | Not started
E22-BL-010 | E22-F05 |  | Story | As a crew member I want a wallet card that shows my medical certificate and travel vaccination status offline so that I can prove compliance on layover | Status-only card; offline readable; refreshed on sign-in | 5 | H2 | P2 | Mobile | E07, E11 |  | Not started
E22-BL-011 | E22-F05 |  | Story | As a crew member I want roster-aware reminders before my certificate or surveillance is due so that I am never grounded by an expiry | Reminders at 60 / 30 / 7 days; respects rest periods from roster data | 5 | H2 | P3 | Mobile | E15, E25 |  | Not started
E22-BL-012 | E22-F01 |  | Task | Define the device test matrix and crash reporting without PHI | Matrix covers top 10 device models; crash payloads scrubbed and verified | 3 | H1 | P2 | Mobile; QA | – |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty