## Epic Overview
E23 – Interoperability Hub (FHIR, IHE, HL7 v2, national records)
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E23
Epic name | Interoperability Hub (FHIR, IHE, HL7 v2, national records)
Goal | Grow the FHIR R4 and HL7 v2 endpoints of the platform into an interoperability hub: a complete, published FHIR profile set with R5 readiness, FHIR subscriptions, SMART app launch, IHE document and identity profiles, an HL7 v2 interface capability for laboratories and devices, a licensed terminology service, and connectors to national or emirate-level health information exchanges where the law and the employee's consent allow.
Business value | Paper and e-mail reports are the main confidentiality leakage point today (E03 rationale). Electronic exchange shortens referral-to-report time, removes re-keying errors and lets each new partner hospital or laboratory be onboarded in weeks instead of a project. Standards protect against lock-in to any partner's proprietary interface.
In scope | • FHIR R4 profiles (Patient, Encounter, Condition, Observation, ServiceRequest, DocumentReference, Procedure, Consent, Task) published as an implementation guide; R5 readiness • FHIR subscriptions (R4B / R5 backport) for partner notifications • SMART on FHIR app launch for approved third-party clinical apps • IHE MHD / XDS.b document exchange, PIXm / PDQm identity, ATNA audit, IUA authorisation • HL7 v2 (ORU, ORM, ADT) interface capability for labs and devices • Terminology service with licensed national editions (D10) • National / emirate-level health information exchange connector (consent-gated, where legally permitted)
Out of scope | • Building partner systems' interfaces • Insurer / ERP / HRIS business connectors (E15 completion) • Regulator medical-certification portals (E24)
Primary stakeholders / roles | Integration architect; Integration team; CMO; DPO; Partner hospitals and laboratories; Procurement (partner contracts); Cyber GRC
Success KPIs | • ≥ 95 % of partner clinical exchanges electronic and standards-based (no e-mail attachments) • Onboarding time for a new FHIR partner ≤ 4 weeks • Referral reports returned electronically ≥ 80 % (supports E04 KPI ≥ 90 % within 7 days) • 100 % conformance-test pass of published profiles • Terminology releases applied within 30 days
Dependencies | E15 Integration (gateway, broker, outbox); E16 Consent and audit; E18 Terminology and master data; E04 / E03 as main consumers
Standards & references | • HL7-FHIR R4 / R4B / R5; HL7-ODH; SMART App Launch 2.x • IHE ITI profiles: MHD, XDS.b, PIXm, PDQm, ATNA, IUA • HL7-V2 v2.5.1 messaging • SNOMED-ICD with licensed national editions • LOCAL-PDP consent for disclosure
Evidence base (why now) | Increment-2 limitations: FHIR Procedure, Consent, Task, ServiceRequest not mapped, no subscriptions; increment 4: ServiceRequest / DocumentReference exchange tested with a simulated partner only (O25); terminology starter subset only (O13, D10); OCR off (D14).
Recommended start horizon | H2 – Scale (months 6–18); spike on national exchange eligibility in H1
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E23 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E23-HLR-01 | The platform shall publish and conform to a FHIR implementation guide covering all resources it exchanges, including Procedure, Consent and Task, and shall be ready to accept FHIR R5 partners. | Partners need a stable contract; missing resources block live hospital exchange. | Must | HL7-FHIR; HL7-ODH | ALL – All subsidiaries & departments (group-wide)
E23-HLR-02 | Partners shall be able to subscribe to relevant events (e.g. referral accepted, report due) through FHIR subscriptions instead of polling or e-mail. | Removes chasing by e-mail; standard notification mechanism. | Should | HL7-FHIR | ALL – All subsidiaries & departments (group-wide)
E23-HLR-03 | Document and identity exchange with hospitals and regional exchanges shall use IHE profiles (MHD / XDS.b, PIXm / PDQm) with ATNA-conformant audit. | Regional exchanges and hospital groups expose IHE profiles; audit must stay end to end. | Should | IHE; ISO27001 | ALL – All subsidiaries & departments (group-wide)
E23-HLR-04 | Laboratories and devices that only speak HL7 v2 shall be connected through a managed interface capability with mapping, acknowledgement and replay. | Many laboratory and audiometry systems still use v2. | Must | HL7-V2; SNOMED-ICD | ALL – All subsidiaries & departments (group-wide)
E23-HLR-05 | Coding shall use a terminology service with licensed national editions and an update runbook. | Starter subset is not safe for production coding; licence per country (R13). | Must | SNOMED-ICD | ALL – All subsidiaries & departments (group-wide)
E23-HLR-06 | Where the law permits and the employee consents, the platform shall retrieve or contribute summary data to a national or emirate-level health information exchange. | Avoids duplicate tests and gives OH clinicians relevant history; must never be default. | Could | LOCAL-PDP; HL7-FHIR | ALL – All subsidiaries & departments (group-wide)

## Feature List
E23 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E23-F01 | Published FHIR implementation guide | Profiles, extensions and examples for every exchanged resource; conformance test suite in CI; R5 mapping layer. | Integration architect | Must | E23-HLR-01 | IG published; conformance tests pass; Procedure, Consent, Task mapped. | None
E23-F02 | FHIR subscriptions | Topic-based subscriptions with content-free notifications and authorised fetch. | Integration team; Partners | Should | E23-HLR-02 | Partner receives referral-status notifications; payload carries no clinical content. | Partner org binding (org_scope) applies.
E23-F03 | IHE document and identity profiles | MHD / XDS.b document source and consumer, PIXm / PDQm identity, ATNA audit forwarding, IUA tokens. | Integration team | Should | E23-HLR-03 | Connectathon-style test with a reference implementation passes. | Depends on the target exchange's profile set.
E23-F04 | HL7 v2 interface capability | Managed v2 interface (MLLP over TLS / VPN) with mapping, ACK / NACK, replay and monitoring. | Integration team; Laboratory | Must | E23-HLR-04 | ORU results from a live laboratory flow into the pull queue; NACKs alert. | Toxicology LIMS uses its own bound API (E10).
E23-F05 | Terminology service | Terminology server with licensed national editions, value-set management and update runbook. | CMO; Integration team | Must | E23-HLR-05 | Licensed edition loaded per environment; search ≤ 300 ms at load. | Licence per operating country (D10).
E23-F06 | National health information exchange connector | Consent-gated query / contribute connector for one national or emirate-level exchange. | DPO; CMO; Integration team | Could | E23-HLR-06 | Pilot with explicit consent; every query in the disclosure log. | Eligibility and onboarding vary by exchange.

## Implementation Backlog
E23 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E23-BL-001 | E23-F01 |  | Enabler | Author the WellnessZ FHIR implementation guide (profiles, extensions, examples) and publish it to partners | IG built and versioned; reviewed by two partners | 8 | H2 | P1 | Integration | E15 |  | Not started
E23-BL-002 | E23-F01 |  | Enabler | Map Procedure, Consent and Task resources and add them to the FHIR export and partner API | Round-trip tests; consent resources reflect the consent register | 8 | H2 | P1 | Integration | E16 |  | Not started
E23-BL-003 | E23-F01 |  | Enabler | Conformance test suite for the IG in CI and an R5 compatibility mapping layer | Suite runs per build; R5 test partner exchange passes | 8 | H2 | P2 | Integration; QA | – |  | Not started
E23-BL-004 | E23-F02 |  | Story | As a partner hospital I want to subscribe to referral events so that I stop polling and chasing by e-mail | Topic subscription; content-free notification; authorised fetch | 8 | H2 | P2 | Integration | E04 |  | Not started
E23-BL-005 | E23-F03 |  | Spike | Assess eligibility and profile sets of the national / emirate-level exchanges in the operating countries | Decision memo per country: legal basis, profiles, onboarding effort | 3 | H1 | P2 | Integration; DPO | – |  | Not started
E23-BL-006 | E23-F03 |  | Enabler | Implement MHD document source / consumer and ATNA audit forwarding | Test with reference implementation; audit events reach SIEM | 13 | H2 | P2 | Integration | E16 |  | Not started
E23-BL-007 | E23-F03 |  | Enabler | Implement PIXm / PDQm identity cross-referencing with the HRIS employee identity | Identity matches reviewed; no automatic merge without clinician confirmation | 8 | H3 | P3 | Integration | E15 |  | Not started
E23-BL-008 | E23-F04 |  | Enabler | Managed HL7 v2 interface capability with mapping, ACK / NACK, replay and monitoring | Live ORU flow from one laboratory; replay tested; dashboards | 13 | H2 | P1 | Integration | E15 |  | Not started
E23-BL-009 | E23-F05 |  | Task | Procure terminology licences and load national editions; write the update runbook | Licences on file per environment; runbook tested with one release | 5 | H1 | P1 | Product Owner; Integration | – |  | Not started
E23-BL-010 | E23-F05 |  | Enabler | Connect the terminology registry to a terminology server and value-set management | Search ≤ 300 ms at load; value sets versioned | 8 | H2 | P2 | Integration | E18 |  | Not started
E23-BL-011 | E23-F06 |  | Story | As an OH physician I want to retrieve a consented summary from the national exchange so that I avoid repeating tests | Explicit consent per query; disclosure log entry; pilot with one exchange | 13 | H3 | P3 | Integration; Clinical SME (OH Nurse / Physician) | E16 |  | Not started
E23-BL-012 | E23-F01 |  | Story | As an integration lead I want a partner onboarding kit (sandbox, test data, certificates, checklist) so that a new FHIR partner goes live in ≤ 4 weeks | Kit published; second partner onboarded within 4 weeks | 5 | H2 | P2 | Integration | E29 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty