## Epic Overview
E24 – Aviation Medical Certification & Regulator Interface
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E24
Epic name | Aviation Medical Certification & Regulator Interface
Goal | Give aeromedical examiners an end-to-end certification workflow – examination in the authority's format, assessment, limitation codes, issue or referral to the authority's medical assessor, qualified electronic signature – and an interface to the civil aviation authority's medical system (for example the UK CAA, the UAE GCAA or an EASA member-state authority): through its API where one is offered, otherwise assisted submission with structured export and receipt reconciliation.
Business value | Crew medical certificate lapses ground aircraft and expose the operator; double entry into the authority's portal costs AME time and causes transcription errors. Qualified signatures give certificates and reports legal effect outside the group (risk R16). A clean regulator interface is a differentiator few OH platforms offer for airlines.
In scope | • Authority examination and report formats (pilot class 1 / 2, cabin crew medical report, ATCO where applicable) as versioned templates • Limitation codes, referral to the authority's medical assessor, certificate issue / deferral / denial states • Qualified or advanced electronic signature through a trust service provider (D12) • Authority interface: API submission where offered; otherwise assisted submission, receipt capture and reconciliation • AME credential and designation tracking; audit of every submission; status-only feed to crew licensing and rostering
Out of scope | • Acting as the authority's system of record • Medical assessor decisions (authority) • Licensing of flight crew beyond medical status
Primary stakeholders / roles | AME lead; AMEs; CMO; Crew licensing (CREW_LICENSING); Crew scheduling; DPO; Legal; the civil aviation authority's medical section
Success KPIs | • Crew medical certificate lapses = 0 (E07 KPI) • ≥ 98 % of examinations submitted to the authority within its deadline • < 2 % of submissions rejected for format or data errors • AME administrative time per examination −20 % (indicative, to be baselined) • 100 % of documents with external legal effect signed with an advanced or qualified signature
Dependencies | E05 Fitness (crew assessment, status feed); E07 Surveillance (crew certificates); E15 Integration (authority gateway); E16 Identity / signature; E23 Interoperability (FHIR / document exchange)
Standards & references | • EASA-MED Part-MED (Reg (EU) 1178/2011 Annex IV); ICAO-A1 Ch. 6; ICAO-8984 • UK CAA and UAE GCAA medical requirements as LOCAL-OHS • eIDAS-style advanced / qualified electronic signatures • LOCAL-PDP medical confidentiality
Evidence base (why now) | Increment-2 sign-off S9: CAA report layouts and limitation-code labels draft; O19: CAA confirmation of crew medical examination formats; R16: simple electronic signature may not be accepted by the CAA or courts; D12 recommends qualified signing for documents with external effect.
Recommended start horizon | H1 – confirm authority formats and interface options (spike); H2 – build
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E24 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E24-HLR-01 | AMEs shall complete examinations and reports in the authority's current formats, held as versioned templates with limitation codes, and record the certification outcome (issue, defer, refer, deny). | Formats are pending authority confirmation; outcome states drive crew availability. | Must | EASA-MED; ICAO-A1; LOCAL-OHS | FLT – Flight Operations; CAB – Cabin Services
E24-HLR-02 | Certificates and reports with legal effect outside the group shall carry an advanced or qualified electronic signature from a trust service provider. | Risk R16; decision D12. | Must | EASA-MED; LOCAL-PDP | FLT – Flight Operations; CAB – Cabin Services
E24-HLR-03 | Examinations and reports shall be submitted to the authority electronically through its API where available, otherwise by assisted submission with structured export, receipt capture and reconciliation. | Removes double entry; regulator interfaces differ by country. | Must | EASA-MED; LOCAL-OHS | FLT – Flight Operations; CAB – Cabin Services
E24-HLR-04 | The platform shall track AME designations, credentials and audit history, and block certification by an AME whose designation has lapsed. | Authority oversight of AMEs; IOSA crew-fitness standards. | Should | EASA-MED; IOSA | FLT – Flight Operations; CAB – Cabin Services
E24-HLR-05 | Crew licensing and rostering shall receive the certificate status and validity only – never clinical content – within 15 minutes of a change. | Status-only disclosure rule; E05 KPI. | Must | EASA-MED; LOCAL-PDP | FLT – Flight Operations; CAB – Cabin Services

## Feature List
E24 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E24-F01 | Authority examination templates | Versioned templates per authority and class, limitation-code catalogue, outcome states, AME / CMO sign-off. | AME; CMO | Must | E24-HLR-01 | Formats confirmed in writing by the authority; outcome states drive certificate validity. | One template set per operating country.
E24-F02 | Advanced / qualified electronic signature | Signature adapter to a trust service provider; signature validation on import; long-term validation. | AME; Legal | Must | E24-HLR-02 | Signed PDF validates in a standard verifier; long-term validation profile. | Internal documents keep the simple signature.
E24-F03 | Authority submission gateway | Gateway adapter per authority: API client or assisted-submission package, receipt capture, reconciliation queue, deadline timers. | AME; Integration team | Must | E24-HLR-03 | Submissions tracked to receipt; overdue items escalate; reconciliation report weekly. | API availability differs by authority.
E24-F04 | AME designation management | Designation, credentials, expiry alerts and a certification guard. | AME lead; Crew licensing | Should | E24-HLR-04 | Expired designation blocks sign-off; alert 60 days before expiry. | None
E24-F05 | Status-only certificate feed | Certificate status and validity to crew licensing and rostering via the outbox; acknowledgement tracking. | Crew licensing; Crew scheduling | Must | E24-HLR-05 | Feed within 15 min; payload passes the outbound allow-list. | Reuses the E05 roster-feed pattern.

## Implementation Backlog
E24 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E24-BL-001 | E24-F01 |  | Spike | Confirm current examination and report formats and interface options with each authority (API, portal, file) | Written confirmation per authority; interface option matrix | 3 | H1 | P1 | Product Owner; AME lead | – |  | Not started
E24-BL-002 | E24-F01 |  | Story | As an AME I want the class 1 / class 2 and cabin crew templates in the authority's format so that I do not transcribe into the portal | Templates versioned per authority; validation of mandatory fields | 8 | H2 | P1 | Clinical SME (OH Nurse / Physician); Platform / Backend | E03 |  | Not started
E24-BL-003 | E24-F01 |  | Story | As an AME I want to record issue, defer, refer or deny with limitation codes so that crew availability is correct the moment I sign | Outcome states; limitation catalogue; validity calculated | 5 | H2 | P1 | Platform / Backend | E07 |  | Not started
E24-BL-004 | E24-F02 |  | Spike | Select the trust service provider for advanced / qualified signatures (D12), including in-country processing | Decision record; DPA; residency confirmed | 3 | H1 | P1 | Security & Privacy; Legal | E16 |  | Not started
E24-BL-005 | E24-F02 |  | Enabler | Signature adapter with long-term validation for externally effective documents | Signed documents validate in a standard verifier; tests for revoked certificates | 8 | H2 | P1 | Platform / Backend | E16 |  | Not started
E24-BL-006 | E24-F03 |  | Enabler | Authority gateway SPI with an API client for the first authority that offers one | Submission and receipt round-trip in the authority's test environment | 13 | H2 | P1 | Integration | E15 |  | Not started
E24-BL-007 | E24-F03 |  | Story | As an AME I want an assisted-submission package and receipt capture where the authority offers only a portal | Structured export; receipt number captured; reconciliation queue | 8 | H2 | P2 | Integration; Frontend / UX | E15 |  | Not started
E24-BL-008 | E24-F03 |  | Story | As the AME lead I want deadline timers and escalation for unsubmitted examinations | Overdue items escalate to AME lead; dashboard | 3 | H2 | P2 | Platform / Backend | E18 |  | Not started
E24-BL-009 | E24-F04 |  | Story | As crew licensing I want AME designations tracked so that only valid AMEs certify | Guard blocks expired designation; 60-day alert | 5 | H2 | P2 | Platform / Backend | E18 |  | Not started
E24-BL-010 | E24-F05 |  | Story | As crew scheduling I want certificate status and validity within 15 minutes, without clinical detail | Status feed; acknowledgement; allow-list test | 5 | H2 | P1 | Integration | E05, E15 |  | Not started
E24-BL-011 | E24-F05 |  | Task | Agree with the authority and crew licensing the reconciliation process for authority-issued decisions | Process signed; monthly reconciliation report | 2 | H2 | P2 | Product Owner; Crew licensing | – |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty