## Epic Overview
E25 – Fatigue Risk & Shift-Work Health (FRMS integration)
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E25
Epic name | Fatigue Risk & Shift-Work Health (FRMS integration)
Goal | Connect occupational health with the airline's Fatigue Risk Management System and rostering without operating the FRMS: fatigue reports with a health component reach OH with the employee's consent, OH restrictions that affect duty patterns (for example no night duty) reach rostering as status, aggregated health-related fatigue insight goes to the FRMS safety action group with suppression, and shift workers get a governed sleep-health screening and referral pathway.
Business value | Fatigue is a recognised flight-safety hazard and a driver of MSK injury, absence and psychological strain in shift work. Today the FRMS and OH work in silos; the CREW_FATIGUE triage protocol has no red-flag question. Joining them safely improves both safety and health outcomes while keeping the non-punitive reporting culture.
In scope | • Consent-based referral from FRMS fatigue reports to OH (health component only) • Duty-pattern restrictions to rostering as status (extends the E05 feed) • Aggregated, suppressed health-fatigue indicators for the FRMS safety action group • Sleep-health screening and referral pathway for shift workers and crew (instruments under clinical governance) • Fatigue-related absence and injury trend analytics (via E26) • Red-flag review of the CREW_FATIGUE triage protocol
Out of scope | • FRMS operations, bio-mathematical fatigue modelling and flight-time limitation compliance (Flight Ops SMS – client E12 out of scope) • Rostering optimisation
Primary stakeholders / roles | FRMS manager / safety action group; Flight Ops; Crew scheduling; Ground operations shift managers; CMO; AME; Nursing Head; Mental-health lead; Employee representatives / unions
Success KPIs | • ≥ 95 % of consented health-related fatigue reports reach OH within 24 h • 100 % of duty-pattern restrictions delivered to rostering within 15 min • ≥ 90 % of positive sleep screens followed up within 10 working days • Fatigue-related sickness absence and injury rate in targeted units: downward trend (indicative) • 0 identifiable data in FRMS aggregates (k ≥ 5)
Dependencies | E02 Triage (CREW_FATIGUE protocol); E05 Fitness (restrictions, roster feed); E09 Psychosocial risk; E12 fatigue & sleep campaigns; E15 Integration (FRMS, rostering); E26 Data platform
Standards & references | • ICAO-A6 and ICAO Doc 9966 FRMS manual • EASA ORO.FTL.120 FRMS (benchmark) • ISO45001; ISO45003 (shift work as psychosocial hazard) • LOCAL-PDP
Evidence base (why now) | Client E12 out of scope: 'Fatigue Risk Management System operations (Flight Ops SMS)' and E12 scope 'fatigue / sleep education and referral (complements FRMS)'; increment-1 limitation: CREW_FATIGUE triage protocol has no red-flag question; E09-HLR-05 psychosocial risk includes shift / fatigue; seeded E12 campaign 'fatigue & sleep'.
Recommended start horizon | H2 – Scale (months 6–18), after rostering transport (E15) and the data platform (E26) are live
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E25 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E25-HLR-01 | When an employee consents, a fatigue report with a health component raised in the FRMS shall create an OH referral containing only the minimum data, without returning clinical content to the FRMS. | Joins safety and health while preserving non-punitive reporting. | Must | ICAO-A6; LOCAL-PDP | FLT – Flight Operations; CAB – Cabin Services; GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E25-HLR-02 | OH restrictions that affect duty patterns (night work, duty length, time-zone crossings) shall reach rostering as coded status within 15 minutes. | Restrictions must be enforced by rostering; extends the status-only feed. | Must | EASA-MED; ICAO-A6 | FLT – Flight Operations; CAB – Cabin Services; GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E25-HLR-03 | The FRMS safety action group shall receive aggregated, suppressed indicators of health-related fatigue by fleet, base or unit. | Systemic insight without identifying individuals. | Should | ICAO-A6; ISO45003 | FLT – Flight Operations; CAB – Cabin Services; GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E25-HLR-04 | Shift workers and crew shall have access to a sleep-health screening and referral pathway using instruments approved by clinical governance. | Sleep disorders are under-diagnosed in shift work and affect fitness. | Should | ISO45001; ILO-C161 | ALL – All subsidiaries & departments (group-wide)
E25-HLR-05 | The CREW_FATIGUE triage protocol shall have clinically approved red-flag criteria and a pathway to AME review where fitness may be affected. | Increment-1 limitation; safety-critical gap. | Must | EASA-MED; ICAO-A1 | FLT – Flight Operations; CAB – Cabin Services

## Feature List
E25 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E25-F01 | FRMS-to-OH consented referral | Inbound FRMS event with consent token, minimal dataset, referral creation, acknowledgement without clinical content. | FRMS manager; OH nurse; Employee | Must | E25-HLR-01 | Referral created only with consent; FRMS receives 'received' status only. | Union consultation before go-live.
E25-F02 | Duty-pattern restriction codes in the roster feed | Restriction codes for night work, duty length and time zones in the restriction catalogue and the status-only feed. | Physician; AME; Crew scheduling | Must | E25-HLR-02 | Codes delivered within 15 min; acknowledgement tracked. | Ground rostering systems included.
E25-F03 | Aggregated fatigue-health indicators | Suppressed indicators by fleet / base / unit published to the FRMS group via the data platform. | FRMS manager; CMO | Should | E25-HLR-03 | Indicators suppressed below k = 5; quarterly publication. | No individual-level data leaves OH.
E25-F04 | Sleep-health pathway | Self-screen in the app, scoring under governance, referral to OH or sleep service, follow-up tracking. | Employee; OH nurse; Physician | Should | E25-HLR-04 | Positive screens followed up within 10 working days; instruments licensed and approved. | Instrument choice by CMO.
E25-F05 | CREW_FATIGUE red-flag review | Clinical review of the protocol, red-flag questions, AME routing. | CMO; AME lead | Must | E25-HLR-05 | Approved protocol version live; red flag routes to AME queue. | None

## Implementation Backlog
E25 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E25-BL-001 | E25-F05 |  | Task | Clinically review the CREW_FATIGUE triage protocol and add approved red-flag questions | New protocol version APPROVED by CMO; tests updated | 3 | H1 | P1 | Clinical SME (OH Nurse / Physician) | E02 |  | Not started
E25-BL-002 | E25-F01 |  | Spike | Agree the FRMS interface, consent model and minimal dataset with the FRMS manager and employee representatives | Interface specification and consent text approved | 3 | H2 | P1 | Product Owner; Integration | – |  | Not started
E25-BL-003 | E25-F01 |  | Story | As a crew member who files a fatigue report I want to choose whether OH contacts me so that health help never feels punitive | Consent choice in the FRMS hand-off; referral only with consent | 8 | H2 | P1 | Integration; Frontend / UX | E15, E16 |  | Not started
E25-BL-004 | E25-F01 |  | Enabler | Inbound FRMS referral endpoint bound to the FRMS client with minimal dataset and content-free acknowledgement | org_scope-bound client; allow-list on response; idempotent | 5 | H2 | P1 | Integration | E15 |  | Not started
E25-BL-005 | E25-F02 |  | Story | As a physician I want duty-pattern restriction codes so that rostering stops assigning night duty or long sectors when I advise against it | Codes in restriction catalogue; feed within 15 min; acknowledgement | 5 | H2 | P1 | Platform / Backend | E05 |  | Not started
E25-BL-006 | E25-F03 |  | Story | As the FRMS manager I want quarterly health-related fatigue indicators by fleet and base so that the safety action group sees systemic issues | Suppressed indicators; definitions approved by CMO and FRMS manager | 5 | H2 | P2 | Data & Analytics | E26 |  | Not started
E25-BL-007 | E25-F04 |  | Task | Select and licence sleep-health screening instruments and set cut-offs under clinical governance | Instruments approved; licences recorded; translations per E21 | 2 | H2 | P2 | Clinical SME (OH Nurse / Physician) | E21 |  | Not started
E25-BL-008 | E25-F04 |  | Story | As a shift worker I want to self-screen my sleep health in the app and get a referral if needed | Screen scored server-side; positive screen creates follow-up task | 8 | H2 | P2 | Frontend / UX; Platform / Backend | E13 |  | Not started
E25-BL-009 | E25-F04 |  | Story | As an OH nurse I want positive sleep screens in a work queue with a 10-day target | Queue with SLA timer; outcome recorded | 3 | H2 | P2 | Platform / Backend | E02 |  | Not started
E25-BL-010 | E25-F03 |  | Story | As a Nursing Head I want fatigue-related absence and injury trends by unit | Trend from the data platform; suppression applied | 3 | H2 | P3 | Data & Analytics | E26 |  | Not started
E25-BL-011 | E25-F01 |  | Task | Consult employee representatives and publish the non-punitive principle for fatigue referrals | Consultation record; principle published in the app | 2 | H2 | P1 | Change & Training | – |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty