## Epic Overview
E26 – Data Platform & Research-Grade De-identified Datasets
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E26
Epic name | Data Platform & Research-Grade De-identified Datasets
Goal | Extend E17 into a governed, in-country data platform: change-data capture from the outbox and module schemas into an analytics store in the same jurisdiction, purpose-specific pseudonymisation, tiered de-identification (operational KPIs, management analytics, research-grade datasets), a semantic KPI layer for every client epic KPI, data quality rules, lineage and a catalogue, and a trusted research environment with ethics approval for de-identified studies.
Business value | Many client KPIs are not reported today (RTW within 5 days, documentation time, litigated-claim trend, campaign ROI, absence as an insight source). Without them the business case of the programme cannot be proven. A governed platform is also the precondition for any predictive model (E27) and the workforce digital twin (E30).
In scope | • CDC / outbox-based pipeline into an in-country analytics store (no export outside the jurisdiction) • Pseudonymisation with purpose-specific keys; de-identification tiers and release rules • Semantic KPI layer for all client epic KPIs, with small-cell suppression inherited • Data quality rules, lineage, catalogue and data contracts with each module • Trusted research environment for de-identified datasets with ethics / DPO approval • Read-only reporting role (O7) and BI access for approved audiences
Out of scope | • Predictive models (E27) • Enterprise HR analytics outside OH • Any person-level OH data for managers or HR
Primary stakeholders / roles | Data product owner; DPO; CMO; Nursing Head; Finance (ROI); Health promotion lead; Cyber GRC; Research / ethics committee
Success KPIs | • 100 % of client epic KPIs (E01–E14) reported from one semantic layer with definitions signed off • Data freshness ≤ 1 h for operational dashboards, ≤ 24 h for analytics • Data-quality rule pass rate ≥ 98 % on critical fields • 0 re-identification incidents; 100 % of releases with a documented de-identification assessment • Research dataset request turnaround ≤ 20 working days
Dependencies | E15 Integration (CDC / broker); E16 Identity, consent and keys; E17 Analytics (de-identified view, KPI API, suppression); E18 Master data (definitions, org hierarchy)
Standards & references | • ISO20889 privacy-enhancing de-identification techniques • ISO25012 data quality model • LOCAL-PDP (GDPR Art. 5, 9, 25, 89 as benchmark) • ISO27701 privacy information management • HL7-ODH for occupational data
Evidence base (why now) | Architecture doc: 'the data-warehouse feed and predictive models' not delivered; O7 read-only reporting role; release notes: RTW-within-5-days, matched-duty rate and documentation time not reported (inc 2), litigated-claim trend (inc 4), ROI not computed and absence not an insight source (inc 5, E12-HLR-01, E12-F05 partial).
Recommended start horizon | H1 – pipeline and KPI layer for the outstanding KPIs; H2 – research environment and de-identified datasets
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E26 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E26-HLR-01 | Analytical data shall flow from the operational platform to an analytics store hosted in the same jurisdiction through change-data capture or the outbox, without manual extracts. | Residency and auditability; manual extracts are a leakage risk. | Must | LOCAL-PDP; ISO27001 | ALL – All subsidiaries & departments (group-wide)
E26-HLR-02 | Personal identifiers shall be replaced by purpose-specific pseudonyms before data reaches the analytics store; re-linking shall be possible only through a controlled, audited service. | Data minimisation and purpose limitation for special-category data. | Must | ISO20889; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E26-HLR-03 | Every client epic KPI shall have a signed-off definition in a semantic layer and be reported with small-cell suppression (k ≥ 5) to its audience. | Business case evidence; consistent definitions across subsidiaries. | Must | ISO45001; HIMSS | ALL – All subsidiaries & departments (group-wide)
E26-HLR-04 | Data quality, lineage and a data catalogue shall be maintained, with data contracts between each module and the platform. | Analytics and models are only as good as the data; contracts prevent silent breakage. | Should | ISO25012 | ALL – All subsidiaries & departments (group-wide)
E26-HLR-05 | De-identified research datasets shall be released only into a trusted research environment after a documented re-identification risk assessment, DPO approval and, where applicable, ethics approval. | Enables evidence-based OH (e.g. MSK, fatigue, exposure studies) without exposing individuals. | Should | ISO20889; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)

## Feature List
E26 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E26-F01 | In-country analytics pipeline | CDC / outbox connectors, landing and curated zones, schema evolution, replay; analytics store in the same region pair. | Data engineers; SRE | Must | E26-HLR-01 | Freshness targets met; pipeline replay tested; no resource outside the jurisdiction. | None
E26-F02 | Pseudonymisation and de-identification service | Purpose-specific HMAC keys, tokenisation, generalisation and suppression rules, controlled re-linking service with audit. | Privacy engineer; DPO | Must | E26-HLR-02 | No direct identifier in the analytics store; re-link requires approved purpose and is audited. | Restricted classes (E09 / E10) aggregate-only by default.
E26-F03 | Semantic KPI layer and dashboards | KPI definitions as code, suppressed aggregates, dashboards per audience (CMO, Nursing Head, HSE, Finance, subsidiaries). | Data product owner; KPI owners | Must | E26-HLR-03 | All client KPIs live with signed definitions; suppression tests pass. | Subsidiary roll-ups follow org_scope.
E26-F04 | Data quality, lineage and catalogue | Quality rules on critical fields, lineage from source to KPI, catalogue with owners and classifications, data contracts. | Data engineers; Module teams | Should | E26-HLR-04 | ≥ 98 % rule pass; lineage visible for every KPI; contract breaks fail CI. | None
E26-F05 | Trusted research environment | Isolated workspace, approved de-identified extracts, output checking, ethics / DPO workflow. | DPO; Research lead; CMO | Should | E26-HLR-05 | First study released after risk assessment; outputs checked before leaving the environment. | No linkage with external data without approval.

## Implementation Backlog
E26 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E26-BL-001 | E26-F01 |  | Enabler | Provision the in-country analytics store and landing / curated zones with infrastructure as code | Store in the approved region pair; CMK; private networking; policy compliant | 8 | H1 | P1 | Data & Analytics; SRE / Platform | E20 |  | Not started
E26-BL-002 | E26-F01 |  | Enabler | CDC / outbox pipeline for the case kernel and modules E01–E08 with replay and schema-evolution handling | Freshness ≤ 1 h; replay tested; schema change does not break pipeline | 13 | H1 | P1 | Data & Analytics | E15 |  | Not started
E26-BL-003 | E26-F01 |  | Enabler | Extend the pipeline to E09–E14 with restricted-class aggregation at source | Restricted classes arrive aggregated only; verified by test | 8 | H2 | P2 | Data & Analytics | E16 |  | Not started
E26-BL-004 | E26-F02 |  | Enabler | Purpose-specific pseudonymisation service with key separation and audited re-linking | Different pseudonyms per purpose; re-link requires approved purpose; audit chain entries | 8 | H1 | P1 | Security & Privacy; Data & Analytics | E16 |  | Not started
E26-BL-005 | E26-F02 |  | Task | De-identification standard: tiers, generalisation rules, suppression, release checklist – approved by the DPO | Standard approved; applied to first two releases | 3 | H1 | P1 | Security & Privacy; DPO | – |  | Not started
E26-BL-006 | E26-F03 |  | Story | As the CMO I want the outstanding KPIs (RTW within 5 days, matched-duty rate, documentation time, litigated-claim trend) so that I can evidence the programme's benefits | KPIs live with signed definitions and suppression | 8 | H1 | P1 | Data & Analytics | E17 |  | Not started
E26-BL-007 | E26-F03 |  | Story | As the health promotion lead I want cost per participant and per outcome so that campaign ROI can be reported (E12-F05 gap) | ROI metrics computed from budget and outcomes; finance-approved definition | 5 | H2 | P2 | Data & Analytics | E12 |  | Not started
E26-BL-008 | E26-F03 |  | Story | As a Nursing Head I want absence intelligence as a campaign insight source without person-level data (E12-HLR-01 gap) | Absence aggregates available to the insight rules via the analytics layer; suppression applied | 5 | H2 | P2 | Data & Analytics | E06, E12 |  | Not started
E26-BL-009 | E26-F04 |  | Enabler | Data-quality rules on critical fields and lineage from source to KPI | Rule pass rate dashboard; lineage graph for every KPI | 8 | H2 | P2 | Data & Analytics | – |  | Not started
E26-BL-010 | E26-F04 |  | Enabler | Data contracts between modules and the platform with contract tests in CI | Breaking change fails the producing module's build | 5 | H2 | P2 | Platform / Backend; Data & Analytics | – |  | Not started
E26-BL-011 | E26-F05 |  | Enabler | Trusted research environment with output checking | Isolated workspace; no internet egress; output review workflow | 8 | H2 | P3 | Data & Analytics; SRE / Platform | E19 |  | Not started
E26-BL-012 | E26-F05 |  | Task | Research data access process with DPO and ethics committee, including re-identification risk assessment template | Process approved; first request handled within 20 working days | 3 | H2 | P3 | DPO; Product Owner | – |  | Not started
E26-BL-013 | E26-F03 |  | Enabler | Read-only reporting database role and governed BI access (O7) | Role grants only analytics views; access reviewed quarterly | 3 | H1 | P1 | Platform / Backend | E16 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty