## Epic Overview
E27 – Predictive Health & Absence Analytics (governed)
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E27
Epic name | Predictive Health & Absence Analytics (governed)
Goal | Use the governed data platform to give OH clinicians advisory early-intervention signals – risk of an absence becoming long-term, return-to-work delay against duration guidelines, likely surveillance non-attendance, MSK hotspot forecasts – with a human in the loop for every action, a clinical safety case, model governance, bias testing, regulatory classification and in-country training and hosting.
Business value | Early intervention is the differentiator of leading OH services (client E06 rationale). If a governed model helps clinicians contact the right employee a week earlier, lost workdays and claim costs fall. The value only materialises if clinicians trust the signals and employees trust the use of their data – hence governance first.
In scope | • Use-case selection with clinicians; silent (shadow) evaluation before any live use • Models for long-term absence risk, RTW delay, surveillance non-attendance and MSK hotspot forecasting • Clinician-facing explanations; advisory only; outcome feedback loop • Model governance: model cards, validation, bias and drift monitoring, change control, decommissioning • Clinical safety case (DCB0129 / DCB0160-style) and DPIA; regulatory classification (EU AI Act style) • In-country training and inference; no PHI to external services
Out of scope | • Any automated decision about an individual (fitness, employment, discipline) • Any individual-level prediction visible to managers, HR or rostering • Insurance or claims-reserving models
Primary stakeholders / roles | CMO; Clinical safety officer; DPO; Data product owner; Data scientists; Nursing Head; Cyber GRC; Employee representatives; Legal
Success KPIs | • Silent-pilot discrimination at or above the threshold agreed in the clinical safety case (e.g. AUROC ≥ 0.75, indicative) • ≥ 70 % of signals rated useful by clinicians in the pilot • Long-term absence conversion −10 % in pilot units vs comparison units (indicative, to be validated) • Performance gap between protected groups ≤ 5 points; 0 unresolved bias findings • 100 % of signals reviewed by a clinician before any contact
Dependencies | E26 Data platform (prerequisite); E06 Absence; E05 Fitness / RTW; E16 Consent, ABAC and audit; E19 Security; decision on AI governance board
Standards & references | • EU-AI-ACT (Reg (EU) 2024/1689) risk classification as benchmark; local AI regulation • DCB0129 / DCB0160 clinical risk management (benchmark) • ISO42001 AI management system; ISO23894 AI risk management; NIST AI RMF • LOCAL-PDP incl. GDPR Art. 22 and 35 as benchmark
Evidence base (why now) | Architecture doc: 'governed predictive models' not delivered; HIMSS DHI (client standard) includes predictive analytics; client E06 rationale: proactive case management (early intervention) is the differentiator; E06 early-intervention queue already exists with rule-based triggers.
Recommended start horizon | H2 – governance, use-case selection and silent pilot; H3 – live advisory use in pilot units, then scale
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E27 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E27-HLR-01 | Predictive outputs shall be advisory only, shown to authorised OH clinicians, and require a clinician's review before any contact or action; no automated decision shall be made about an individual. | Human oversight; GDPR Art. 22-type rights; trust. | Must | EU-AI-ACT; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E27-HLR-02 | Each model shall have a clinical safety case, a DPIA, a model card and a regulatory classification approved before live use. | Health and employment contexts can be high-risk under AI regulation. | Must | DCB0129; EU-AI-ACT; ISO42001 | ALL – All subsidiaries & departments (group-wide)
E27-HLR-03 | Models shall be validated in a silent pilot and monitored in use for performance, calibration, drift and bias across subsidiaries and protected groups. | Prevents harm from biased or decaying models. | Must | ISO23894; NIST-AI-RMF | ALL – All subsidiaries & departments (group-wide)
E27-HLR-04 | Training and inference shall run in-country on pseudonymised data; no personal health data shall be sent to an external model service. | Residency and special-category data rules. | Must | LOCAL-PDP; ISO27001 | ALL – All subsidiaries & departments (group-wide)
E27-HLR-05 | Employees shall be told how predictive signals are used, and the use shall be covered by the privacy notice and works-council / employee-representative consultation where required. | Transparency and legitimacy. | Must | LOCAL-PDP; EU-AI-ACT | ALL – All subsidiaries & departments (group-wide)
E27-HLR-06 | Aggregate forecasts (e.g. MSK hotspots, surveillance demand) shall be available to prevention and planning roles with suppression. | Population-level value without individual exposure. | Should | ISO45001 | ALL – All subsidiaries & departments (group-wide)

## Feature List
E27 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E27-F01 | AI governance and clinical safety | AI governance board, clinical safety case, DPIA, model cards, classification, change control. | Clinical safety officer; DPO; CMO | Must | E27-HLR-02 | Board chartered; safety case approved before live use. | Applies also to E28.
E27-F02 | Model development and silent pilot | Feature engineering on pseudonymised data, model training in-country, silent evaluation against outcomes. | Data scientists; Clinicians | Must | E27-HLR-03 | Silent-pilot report meets agreed thresholds; bias analysis included. | Restricted classes excluded unless approved.
E27-F03 | Clinician-facing advisory signals | Signals in the E06 early-intervention queue with explanation, confidence and feedback; no exposure outside OH. | OH nurse; Physician | Must | E27-HLR-01 | Signals visible to OH roles only; review recorded before action; feedback captured. | Pilot units only at first.
E27-F04 | Model monitoring and lifecycle | Performance, calibration, drift and fairness monitoring; retraining under change control; decommissioning. | Data scientists; Clinical safety officer | Must | E27-HLR-03 | Monthly monitoring report; alert on drift; retraining approved before release. | None
E27-F05 | Transparency and employee communication | Privacy notice update, employee FAQ, representative consultation, opt-out where required. | DPO; Change & Training | Must | E27-HLR-05 | Notice published before live use; consultation record. | Local law may require opt-out.
E27-F06 | Aggregate forecasts | Suppressed forecasts for MSK hotspots and surveillance demand feeding E12 and E14. | Health promotion lead; Clinic manager | Should | E27-HLR-06 | Forecast error reported; suppression applied. | Feeds E30.

## Implementation Backlog
E27 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E27-BL-001 | E27-F01 |  | Task | Charter the AI governance board (CMO, clinical safety officer, DPO, CISO, legal, employee representative) | Terms of reference; RACI; first meeting held | 2 | H2 | P1 | Product Owner; DPO | – |  | Not started
E27-BL-002 | E27-F01 |  | Task | Clinical safety case and DPIA for the long-term absence risk use case | Hazard log; risk controls; approval by clinical safety officer and DPO | 5 | H2 | P1 | Clinical safety officer; DPO | E26 |  | Not started
E27-BL-003 | E27-F01 |  | Spike | Regulatory classification of each use case under the applicable AI regulation and local law | Classification memo per use case with obligations | 3 | H2 | P1 | Legal; Security & Privacy | – |  | Not started
E27-BL-004 | E27-F02 |  | Enabler | Feature store on pseudonymised data in the in-country analytics platform | Features documented; no direct identifiers; lineage | 8 | H2 | P1 | Data & Analytics | E26 |  | Not started
E27-BL-005 | E27-F02 |  | Story | As the CMO I want a silent pilot of long-term absence risk against real outcomes so that we only go live if it helps | 6-month silent run; report on discrimination, calibration, fairness | 13 | H2 | P1 | Data & Analytics | E06 |  | Not started
E27-BL-006 | E27-F02 |  | Story | As a Nursing Head I want an RTW-delay signal against duration guidelines so that stalled cases are reviewed earlier | Silent evaluation; threshold agreed; explanation available | 8 | H3 | P2 | Data & Analytics | E05 |  | Not started
E27-BL-007 | E27-F03 |  | Story | As an OH nurse I want advisory risk signals in my early-intervention queue with the main contributing factors so that I can decide whether to call | Signal, explanation and confidence shown to OH roles only; review recorded | 8 | H3 | P1 | Frontend / UX; Data & Analytics | E06, E16 |  | Not started
E27-BL-008 | E27-F03 |  | Story | As a clinician I want to give feedback on each signal so that the model and its thresholds can be reviewed | Feedback captured; used in monitoring report | 3 | H3 | P2 | Frontend / UX | – |  | Not started
E27-BL-009 | E27-F04 |  | Enabler | Monitoring of performance, calibration, drift and fairness with alerting | Monthly report; drift alert tested | 8 | H3 | P1 | Data & Analytics | E20 |  | Not started
E27-BL-010 | E27-F04 |  | Task | Model change-control and decommissioning procedure | Procedure approved by governance board | 2 | H2 | P2 | Clinical safety officer; Data & Analytics | – |  | Not started
E27-BL-011 | E27-F05 |  | Task | Update privacy notice, employee FAQ and consult representatives before any live use | Notice published; consultation record | 3 | H2 | P1 | DPO; Change & Training | – |  | Not started
E27-BL-012 | E27-F06 |  | Story | As the health promotion lead I want suppressed MSK hotspot forecasts by unit so that campaigns are planned before injuries rise | Forecast with error reported; suppression k ≥ 5 | 5 | H3 | P3 | Data & Analytics | E12 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty