## Epic Overview
E28 – Clinical Documentation Assistant (governed)
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E28
Epic name | Clinical Documentation Assistant (governed)
Goal | Enable the platform's existing, consent-gated documentation-assistant extension point (AiDocumentationProvider) with an in-country, governed provider: dictation or consented ambient capture produces a draft structured note, case summary, handover or referral-letter draft that the clinician edits and signs; assistant involvement is flagged and audited; restricted classes are excluded by default; quality is measured continuously.
Business value | The client E03 KPI targets −30 % documentation time with templates and assistance; the illustrative business case values documentation savings among the largest benefits. Clinician time returned to patients improves access and wait times. The extension point, consent purpose and audit already exist – the remaining work is governance, provider and evaluation.
In scope | • Evaluation spike and DPIA (D13), 5-clinician pilot (increment-2 recommendation), then staged roll-out • In-country provider integration behind AiDocumentationProvider (locally hosted or contracted with DPA and in-country processing) • Dictation and consented ambient capture front end; Arabic and English transcripts • Draft note, case summary, handover and referral-letter drafts; clinician edit and sign-off • Evaluation harness: accuracy, omissions, unsupported statements; monitoring in use • Optional on-host OCR for scanned images (D14) where volumes justify
Out of scope | • Autonomous documentation or coding without clinician sign-off • Use in E09 / E10 restricted classes unless separately approved • Diagnostic decision support beyond existing CDS rules
Primary stakeholders / roles | CMO; Clinical safety officer; DPO; OH physicians and nurses (pilot group); Cyber GRC; Nursing Head; Employee representatives
Success KPIs | • Documentation time per encounter −30 % vs baseline (E03 KPI) • ≥ 80 % of drafts accepted with minor edits in pilot • 0 signed notes containing unreviewed assistant content (audit check) • 100 % of assistant-assisted notes flagged and audited • Employee consent uptake tracked; 0 complaints upheld about assistant use
Dependencies | E03 Record (extension point, consent purpose); E16 Consent and audit; E19 Security (provider assessment); E21 Arabic language support; E27 AI governance board (shared)
Standards & references | • DCB0129 / DCB0160 clinical risk management (benchmark) • EU-AI-ACT transparency obligations as benchmark; ISO42001 • LOCAL-PDP (DPIA, processor DPA, in-country processing) • ISO27001 supplier security
Evidence base (why now) | Increment-2: consent-gated assistant extension point with no provider enabled, no audio capture front end, pilot not run (E03-BL-019); sign-off S11: provider and DPIA pending; decision D13: run the evaluation spike with DPIA before enabling any provider; client E03-HLR-07 requires explicit consent, clinician review and sign-off, and a draft within 60 s.
Recommended start horizon | H1 – evaluation spike and DPIA; H2 – pilot and staged roll-out
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E28 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E28-HLR-01 | The assistant shall only run with the employee's explicit consent for the encounter, and the clinician shall review, edit and sign every draft; nothing is filed without sign-off. | Client E03-HLR-07; clinical accountability. | Must | LOCAL-PDP; DCB0129 | ALL – All subsidiaries & departments (group-wide)
E28-HLR-02 | Audio, transcripts and drafts shall be processed in-country by a provider under a DPA, with no retention or training on the data beyond the agreed purpose. | Special-category data; residency; no PHI to external models without DPA. | Must | LOCAL-PDP; ISO27001 | ALL – All subsidiaries & departments (group-wide)
E28-HLR-03 | Every assistant-assisted note shall be flagged and audited (consent, provider, model version, edits), visible to the clinician and the DPO. | Transparency and traceability. | Must | EU-AI-ACT; ISO42001 | ALL – All subsidiaries & departments (group-wide)
E28-HLR-04 | Draft quality shall be evaluated before roll-out and monitored in use for accuracy, omissions and unsupported statements, with a clinical safety case. | Draft errors are a clinical hazard. | Must | DCB0129; ISO23894 | ALL – All subsidiaries & departments (group-wide)
E28-HLR-05 | The assistant shall support Arabic and English consultations and produce drafts in the clinician's documentation language. | Bilingual consultations are common. | Should | WCAG22 | ALL – All subsidiaries & departments (group-wide)

## Feature List
E28 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E28-F01 | Evaluation, DPIA and provider selection | Evaluation of locally hosted vs contracted in-country options against privacy, accuracy, latency, cost; DPIA. | CMO; DPO; Cyber GRC | Must | E28-HLR-02 | Decision record; DPIA approved; DPA signed if contracted. | Decision D13.
E28-F02 | Capture front end | Dictation and consented ambient capture in the OH workspace and tablet, consent prompt, indicator while capturing. | OH physician; OH nurse | Must | E28-HLR-01 | Capture only after consent; visible indicator; audio discarded after transcription per policy. | Not available in restricted classes.
E28-F03 | Draft generation and sign-off | Provider behind AiDocumentationProvider; draft structured note, summary, handover, referral letter; side-by-side review; sign-off. | OH physician; OH nurse | Must | E28-HLR-01 | Draft within 60 s; edits tracked; unsigned drafts never filed. | Existing SPI and audit reused.
E28-F04 | Assistant transparency and audit | Flag on notes, audit entries with provider and version, DPO report. | DPO; Clinicians | Must | E28-HLR-03 | 100 % of assisted notes flagged; monthly DPO report. | None
E28-F05 | Quality evaluation and monitoring | Evaluation set, clinician rating, error taxonomy, monitoring dashboard, safety case. | Clinical safety officer; CMO | Must | E28-HLR-04 | Pilot report meets thresholds; monitoring live. | Shared AI governance board with E27.

## Implementation Backlog
E28 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E28-BL-001 | E28-F01 |  | Spike | Evaluate locally hosted vs contracted in-country assistant options against privacy, accuracy, latency, Arabic support and cost (D13) | Evaluation report and recommendation | 5 | H1 | P1 | Product Owner; Security & Privacy | E19 |  | Not started
E28-BL-002 | E28-F01 |  | Task | DPIA and clinical safety case for the documentation assistant | DPIA approved by DPO; hazard log approved by clinical safety officer | 5 | H1 | P1 | DPO; Clinical safety officer | – |  | Not started
E28-BL-003 | E28-F01 |  | Task | Contract and DPA with the selected provider, including in-country processing, no retention and no training on WellnessZ data | Signed DPA; security due diligence complete | 2 | H2 | P1 | Procurement; Legal | E19 |  | Not started
E28-BL-004 | E28-F02 |  | Story | As an OH physician I want to dictate or, with consent, capture the consultation so that I can focus on the employee | Consent prompt; capture indicator; audio policy enforced | 8 | H2 | P1 | Frontend / UX | E03 |  | Not started
E28-BL-005 | E28-F03 |  | Enabler | Provider adapter implementing AiDocumentationProvider with timeouts, retries and no PHI in logs | Adapter selected by configuration; draft within 60 s at p95 | 8 | H2 | P1 | Platform / Backend | E03 |  | Not started
E28-BL-006 | E28-F03 |  | Story | As a clinician I want a side-by-side review of the draft structured note before I sign so that I stay accountable for every word | Diff of edits; sign-off required; unsigned drafts expire | 8 | H2 | P1 | Frontend / UX | E03 |  | Not started
E28-BL-007 | E28-F03 |  | Story | As a case manager I want a case summary and handover draft so that cover clinicians get context quickly | Summary drafts from signed notes only; clinician review | 5 | H2 | P2 | Platform / Backend; Frontend / UX | – |  | Not started
E28-BL-008 | E28-F04 |  | Story | As the DPO I want a monthly report of assistant use, consent and flags so that I can evidence lawful use | Report by unit; suppression where needed | 3 | H2 | P2 | Platform / Backend | E16 |  | Not started
E28-BL-009 | E28-F05 |  | Enabler | Evaluation harness with a de-identified evaluation set and error taxonomy | Harness repeatable; results per provider version | 5 | H2 | P1 | Data & Analytics | E26 |  | Not started
E28-BL-010 | E28-F05 |  | Task | Run the 5-clinician pilot and decide on staged roll-out | Pilot report: time saved, acceptance, errors; governance decision | 5 | H2 | P1 | Clinical SME (OH Nurse / Physician); Product Owner | – |  | Not started
E28-BL-011 | E28-F02 |  | Story | As a bilingual clinician I want Arabic consultations transcribed and drafted in English so that the record stays consistent | Arabic audio supported; draft language selectable | 5 | H2 | P3 | Platform / Backend | E21 |  | Not started
E28-BL-012 | E28-F03 |  | Spike | Assess on-host OCR for scanned images (D14) as an input to drafts and search | Volume analysis; recommendation; no cloud OCR without DPA | 2 | H2 | P3 | Platform / Backend | – |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty