## Epic Overview
E29 – Multi-Subsidiary Tenancy, Onboarding & Extension Platform
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E29
Epic name | Multi-Subsidiary Tenancy, Onboarding & Extension Platform
Goal | Make WellnessZ a product the group can roll out to every subsidiary – and potentially to external clients – quickly and safely: a documented tenancy model with options per residency need, automated tenant provisioning, white-label branding, tenant content packs, a signed extension (plug-in) model so client code no longer needs a fork, and governed feature flags.
Business value | Subsidiaries (catering, cargo, duty free, hospitality, engineering) have different hazards and rules; each onboarding today is configuration plus, for code, a fork or client module. A repeatable onboarding factory reduces time to value and keeps all tenants on one upgrade path – the precondition for any commercial offering.
In scope | • Tenancy options: logical tenant in a shared instance (org_scope + tenant configuration), schema-per-tenant, instance-per-tenant for separate jurisdictions • Tenant provisioning automation (IdP realm / groups, configuration, content packs, environments) • White-label branding of the four web apps, documents and notifications • Signed extension model (launcher change, compatibility contract, signing, sandbox rules) • Feature-flag governance and tenant-level enablement • Tenant isolation test suite and upgrade orchestration
Out of scope | • Commercial terms, pricing and contracts • Changing the residency principle (each tenant still in its own jurisdiction)
Primary stakeholders / roles | CIO; Product leadership; Subsidiary OH leads; Platform & SRE team; Architecture; Cyber GRC; DPO; Procurement / commercial
Success KPIs | • New subsidiary onboarded in ≤ 4 weeks from signed scope (indicative target) • 0 cross-tenant data access in the isolation test suite and pen test • ≥ 80 % of client-specific requirements met by configuration or signed extensions, without a fork • All tenants on the current release within one sprint of general availability
Dependencies | E16 Identity (org_scope, realms); E18 Configuration (tenant settings, content packs); E20 SRE (instances, upgrades); E19 Security (extension signing, pen test)
Standards & references | • ISO27001 A.8.3 / A.5.15 information access restriction • SOC2 CC6.1; ISO27017 cloud controls (tenant segregation) • LOCAL-PDP residency per tenant • NIST-SSDF and SLSA for extensions
Evidence base (why now) | Release notes 5: client extension JARs are not implemented (client code = fork / branch or client module); WZ_FEATURE_* flags are plumbing only; decision D22 and open item O34; SPI overrides need @Order to take effect (customisation guide §7); org_scope and subsidiary roll-ups already exist.
Recommended start horizon | H2 – tenancy model decision and onboarding factory; H3 – white-label and extension marketplace
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E29 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E29-HLR-01 | The platform shall define and support tenancy options – logical tenant in a shared instance, schema-per-tenant and instance-per-tenant – selected per residency and contractual need. | Subsidiaries share a jurisdiction; external clients may not. | Must | ISO27017; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E29-HLR-02 | A new tenant shall be provisioned by automation: identity configuration, organisation scope, configuration and content packs, branding and environments. | Repeatable, auditable onboarding in weeks. | Must | SOC2 CC8.1 | ALL – All subsidiaries & departments (group-wide)
E29-HLR-03 | Client-specific code shall be delivered as signed extensions against a published compatibility contract, loaded without forking the product. | Decision D22; forks fragment upgrades. | Should | NIST-SSDF; SLSA | ALL – All subsidiaries & departments (group-wide)
E29-HLR-04 | Tenants shall be able to apply their own branding to the web apps, documents and notifications without code changes. | Subsidiary identity and external clients. | Could | WCAG22 | ALL – All subsidiaries & departments (group-wide)
E29-HLR-05 | Tenant isolation shall be verified continuously by an automated test suite and in each penetration test. | Cross-tenant disclosure is the worst-case failure. | Must | ISO27001; SOC2 CC6.1 | ALL – All subsidiaries & departments (group-wide)
E29-HLR-06 | Feature flags shall be governed (owner, scope, expiry, audit) and enable product features per tenant. | Flags are plumbing only today (O34). | Should | SOC2 CC8.1 | ALL – All subsidiaries & departments (group-wide)

## Feature List
E29 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E29-F01 | Tenancy model and decision record | Options analysis, reference architecture per option, cost and operational impact. | Architecture; CIO | Must | E29-HLR-01 | Decision record approved; isolation controls defined per option. | Residency principle unchanged.
E29-F02 | Tenant provisioning factory | Automation for IdP realm / groups, org_scope, configuration and content packs, branding, environments. | Platform & SRE; Subsidiary OH lead | Must | E29-HLR-02 | Test tenant provisioned end to end in < 1 day of automation time. | Content packs per sector (catering, cargo, retail…).
E29-F03 | Signed extension model | Launcher change, extension API and compatibility contract, signing and verification, extension registry. | Architecture; Platform / Backend | Should | E29-HLR-03 | Unsigned extension refused; sample extension upgrades across two releases without change. | Replaces fork / client module for new clients.
E29-F04 | White-label branding | Theme tokens, logos, document and notification templates per tenant, accessible colour checks. | Frontend / UX | Could | E29-HLR-04 | Branding change without deployment; contrast check passes. | None
E29-F05 | Tenant isolation assurance | Isolation test suite across APIs, analytics, documents and notifications; included in pen test scope. | QA; Security & Privacy | Must | E29-HLR-05 | Nightly suite: 0 cross-tenant access. | Extends the access-control matrix of E19.
E29-F06 | Feature-flag governance | Flag register, tenant scope, expiry, audit and product features reading flags. | Release manager; Product owners | Should | E29-HLR-06 | Every flag has owner and expiry; tenant toggles audited. | Shared with E20 dark launches.

## Implementation Backlog
E29 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E29-BL-001 | E29-F01 |  | Spike | Tenancy options analysis (shared logical, schema-per-tenant, instance-per-tenant) with residency, cost and operations impact | Decision record approved by architecture board and DPO | 5 | H2 | P1 | Platform / Backend; Security & Privacy | E16 |  | Not started
E29-BL-002 | E29-F02 |  | Enabler | Tenant provisioning pipeline: IdP groups / realm, org_scope, configuration, environment overlays | Test tenant provisioned by pipeline; audit trail | 13 | H2 | P1 | SRE / Platform | E18, E20 |  | Not started
E29-BL-003 | E29-F02 |  | Task | Sector content packs (catering, cargo, retail, engineering, hospitality) for hazards, programmes and templates | Packs versioned; approved by CMO / Nursing Head | 5 | H2 | P2 | Clinical SME (OH Nurse / Physician); Product Owner | E18 |  | Not started
E29-BL-004 | E29-F02 |  | Story | As a subsidiary OH lead I want an onboarding checklist and tracker so that go-live in ≤ 4 weeks is predictable | Checklist covering IdP, data, content, training, sign-offs | 3 | H2 | P2 | Product Owner | – |  | Not started
E29-BL-005 | E29-F03 |  | Spike | Design the extension launcher and compatibility contract (D22) with signing and verification | Design approved; threat model per E19 | 5 | H2 | P1 | Platform / Backend | E19 |  | Not started
E29-BL-006 | E29-F03 |  | Enabler | Implement signed extension loading, registry and compatibility checks | Unsigned / incompatible extension refused at start; sample extension works across two releases | 13 | H3 | P2 | Platform / Backend | E19 |  | Not started
E29-BL-007 | E29-F04 |  | Story | As a subsidiary I want my branding on apps, documents and notifications without a deployment | Theme tokens; templates per tenant; contrast checks | 8 | H3 | P3 | Frontend / UX | E21 |  | Not started
E29-BL-008 | E29-F05 |  | Enabler | Tenant isolation test suite (APIs, analytics, documents, notifications) running nightly | Suite in CI; 0 cross-tenant access; added to pen-test scope | 8 | H2 | P1 | QA; Security & Privacy | E19 |  | Not started
E29-BL-009 | E29-F06 |  | Story | As a release manager I want governed feature flags read by product features per tenant | Flag register; tenant scope; expiry; audit | 8 | H2 | P2 | Platform / Backend | E18, E20 |  | Not started
E29-BL-010 | E29-F02 |  | Enabler | Upgrade orchestration so that all tenants move to a new release within one sprint | Wave plan automated; rollback per tenant | 8 | H3 | P2 | SRE / Platform | E20 |  | Not started
E29-BL-011 | E29-F01 |  | Task | Instance-per-tenant reference deployment for a client in another jurisdiction | Reference overlay and runbook; residency verified | 5 | H3 | P3 | SRE / Platform | E20 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty