## Epic Overview
E30 – Workforce Health Digital Twin & Capacity Planning
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E30
Epic name | Workforce Health Digital Twin & Capacity Planning
Goal | Build an aggregate, de-identified model of workforce health readiness – fit and certified crew per base and fleet versus roster need, certificate-expiry horizon, surveillance and immunisation coverage, OH clinic capacity – and use it to simulate scenarios (outbreak at a station, new route to an endemic area, fleet growth, heat season, mass vaccination) so that operations and OH plan capacity before the problem arrives.
Business value | Turns OH from reactive to predictive at the level executives care about: will we have enough fit, certified crew and ground staff, and enough clinic capacity, next quarter? Supports network planning decisions with health evidence while never exposing an individual.
In scope | • Aggregate readiness model per base / fleet / unit from E05, E07, E11 and roster data (suppressed) • Clinic demand and capacity model linked to E14 • Scenario simulation engine with documented assumptions • Executive and operations dashboards; planning exports • Validation of forecasts against actuals
Out of scope | • Individual-level predictions (E27) • Rostering or network optimisation (operations systems)
Primary stakeholders / roles | COO / Network planning; Crew planning; CMO; Nursing Head; Clinic managers; Data product owner; DPO
Success KPIs | • Clinic demand forecast within ± 10 % at month level • Crew unavailability caused by certificate expiry = 0 • Scenario analysis delivered within 1 working day of request • Clinic utilisation ≥ 80 % (E14 KPI) with wait time ≤ 15 min
Dependencies | E26 Data platform; E27 forecasts; E14 Scheduling capacity; E07 Surveillance and certificates; E11 Immunisation; E15 rostering / network data
Standards & references | • ISO45001 planning; ICAO-A6 operator responsibilities • ISO20889 de-identification; LOCAL-PDP • WHO-IHR preparedness
Evidence base (why now) | E14 capacity forecasting exists at clinic level; E11 tracing and campaigns exist; no cross-domain readiness view; outbreak playbook and tabletop exercise outstanding (E11-BL-013); the Tier-0 decision pack values operational disruption avoided (E07 / E05 crew) as a benefit category.
Recommended start horizon | H3 – Ecosystem (months 18–36), once E26 and E27 are live
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E30 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E30-HLR-01 | The platform shall compute aggregate health-readiness indicators per base, fleet and unit (fit, certified, restricted, due) with suppression. | Executive and planning view without individual exposure. | Must | ISO45001; LOCAL-PDP | FLT – Flight Operations; CAB – Cabin Services; GND – Ground Services; CGO – Cargo & Freight; CAT – Catering; ENG – Engineering & Maintenance; SEC – Security, Fire & Rescue
E30-HLR-02 | OH clinic demand and capacity shall be forecast from surveillance due lists, campaigns, case trends and seasonality. | Prevents backlogs that cause certificate lapses. | Must | ISO45001 | ALL – All subsidiaries & departments (group-wide)
E30-HLR-03 | Planners shall be able to simulate scenarios (outbreak, new destination, fleet growth, heat season, mass vaccination) with explicit assumptions. | Preparedness for health events with operational impact. | Should | WHO-IHR; ICAO-A6 | ALL – All subsidiaries & departments (group-wide)
E30-HLR-04 | Forecasts shall be validated against actuals and the error published with every forecast. | Trust in the model. | Must | ISO23894 | ALL – All subsidiaries & departments (group-wide)

## Feature List
E30 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E30-F01 | Aggregate readiness model | Readiness indicators per base / fleet / unit from status data, suppressed. | Crew planning; CMO | Must | E30-HLR-01 | Indicators refreshed daily; suppression k ≥ 5. | Status data only.
E30-F02 | Clinic demand and capacity forecast | Forecast feeding E14 capacity planning and staffing. | Clinic managers; Nursing Head | Must | E30-HLR-02 | Forecast error ± 10 % monthly after two quarters. | None
E30-F03 | Scenario simulation | Scenario engine with templates and documented assumptions; comparison view. | Network planning; CMO | Should | E30-HLR-03 | Five scenario templates; results within 1 working day. | Used in the outbreak tabletop.
E30-F04 | Forecast validation and dashboards | Back-testing, error reporting, executive dashboard. | Data product owner | Must | E30-HLR-04 | Error shown with each forecast; monthly validation report. | None

## Implementation Backlog
E30 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E30-BL-001 | E30-F01 |  | Enabler | Readiness data model from fitness, certificate, surveillance and immunisation statuses joined to roster need | Model documented; suppressed indicators per base / fleet | 8 | H3 | P1 | Data & Analytics | E26 |  | Not started
E30-BL-002 | E30-F01 |  | Story | As crew planning I want certified-crew readiness per base for the next 90 days so that expiries never ground a rotation | 90-day horizon; status only; suppression | 8 | H3 | P1 | Data & Analytics | E07, E24 |  | Not started
E30-BL-003 | E30-F02 |  | Story | As a clinic manager I want a monthly demand forecast by service so that I staff clinics ahead of surveillance peaks | Forecast by service and site; error shown | 8 | H3 | P1 | Data & Analytics | E14, E27 |  | Not started
E30-BL-004 | E30-F02 |  | Story | As the Nursing Head I want staffing recommendations from the forecast | Recommended sessions per site; manual override | 5 | H3 | P2 | Data & Analytics; Frontend / UX | E14 |  | Not started
E30-BL-005 | E30-F03 |  | Enabler | Scenario engine with parameterised templates (outbreak, destination, growth, heat, vaccination) | Five templates; assumptions recorded with results | 13 | H3 | P2 | Data & Analytics | – |  | Not started
E30-BL-006 | E30-F03 |  | Task | Use the scenario engine in the outbreak tabletop exercise (E11-BL-013) | Exercise report with lessons learned | 2 | H3 | P2 | Clinical SME (OH Nurse / Physician); Change & Training | E11 |  | Not started
E30-BL-007 | E30-F04 |  | Enabler | Back-testing and forecast error reporting | Monthly validation report; error displayed on dashboards | 5 | H3 | P1 | Data & Analytics | – |  | Not started
E30-BL-008 | E30-F04 |  | Story | As the COO I want an executive readiness dashboard so that network decisions consider workforce health | Dashboard with suppressed indicators and scenario comparison | 5 | H3 | P2 | Data & Analytics; Frontend / UX | E26 |  | Not started
E30-BL-009 | E30-F01 |  | Task | DPIA for the readiness model and dashboards | DPIA approved; audiences defined | 2 | H3 | P1 | DPO | – |  | Not started
E30-BL-010 | E30-F02 |  | Spike | Assess linking the forecast to E14 diary templates for automatic session proposals | Feasibility memo | 3 | H3 | P3 | Platform / Backend | E14 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty