## Epic Overview
E31 – Employee Wellbeing Marketplace & Benefits Integration
Epic overview, scope, value, KPIs and summary metrics (review with the C-suite sponsor, CIO, CMO / Nursing Head and Cyber GRC)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic ID | E31
Epic name | Employee Wellbeing Marketplace & Benefits Integration
Goal | Offer employees a curated marketplace of wellbeing services – EAP, physiotherapy, sleep, nutrition, smoking cessation, fitness and benefits-provider programmes – inside the employee app, with eligibility from the group's HR / benefits systems, consented hand-off to the vendor, and only aggregated participation and outcomes coming back; WellnessZ does not administer benefits.
Business value | Employees get one trusted front door for wellbeing; the group gets higher participation (E12 KPI ≥ 40 %), a measurable link between prevention spend and outcomes (with E26), and a standard vendor-onboarding route with DPAs and security due diligence.
In scope | • Marketplace catalogue in the employee app with eligibility by subsidiary, role and benefits plan • Vendor onboarding: DPA, security due diligence, API contract, content review • Consented hand-off (deep link / referral token) and aggregate participation / outcome return • Links from OH pathways (e.g. MSK case → physiotherapy offer) without sharing clinical data • Spend and outcome analytics with suppression (via E26)
Out of scope | • Benefits / gym administration and payroll deductions (client E12 out of scope) • Vendor service delivery • Sharing any OH record data with vendors
Primary stakeholders / roles | Health promotion lead; HR / reward; Procurement; DPO; Cyber GRC; EAP partner; Employees
Success KPIs | • Campaign / programme participation ≥ 40 % by unit (E12 KPI) • Vendor onboarding ≤ 6 weeks with DPA and security review • Employee satisfaction with the marketplace ≥ 4 / 5 • 0 health data shared with vendors without explicit consent • Cost per engaged employee reported quarterly
Dependencies | E12 Health promotion (campaign app, wearables); E13 Portal / app; E15 Integration (benefits system, vendor APIs); E16 Consent; E26 Data platform (ROI)
Standards & references | • LOCAL-PDP consent and processor agreements • ISO27001 A.5.19–A.5.22 supplier relationships • ISO45003 wellbeing interventions • WCAG22
Evidence base (why now) | Client E12 out of scope: 'Gym / benefits administration'; E12-F04 campaign app and wearable integration partial (no live app); EAP partner already in the partner portal; ROI metric missing (E12-F05).
Recommended start horizon | H3 – Ecosystem (months 18–36)
Summary metrics (formula-driven)
Number of high-level requirements
Number of features
Number of backlog items
Total story points (indicative)
Story points – H1 (0–6 months)
Story points – H2 (6–18 months)
Story points – H3 (18–36 months)
Indicative team-sprints (at 30 SP per sprint)
Must-have requirements
Backlog items awaiting review decision
Notes & assumptions
How to review: yellow cells are for the reviewers named on the overview (C-suite sponsor, CIO, CMO / Nursing Head, Cyber GRC, DPO). Use the 'Decision' and 'Review comment' columns on each sheet; the dropdowns offer Accept / Modify / Reject / Defer.
Story points are indicative relative-size estimates (Fibonacci-like scale) produced during strategy drafting; they must be re-estimated by the delivery teams. Team-sprints in the catalogue workbook use an indicative velocity of 30 points per team per two-week sprint.
Horizons: H1 = Go-live readiness and close the gaps (months 0–6), H2 = Scale, intelligence and experience (months 6–18), H3 = Ecosystem and industry leadership (months 18–36). Priority on backlog items is P1 (critical) / P2 / P3.
Nothing in this workbook exists in the product today unless the 'Evidence base' row says so; benefits and KPI targets are indicative and must be baselined by their business owners.
Confidentiality rule used throughout: managers, HR, crew scheduling, vendors and analytics audiences see status or suppressed aggregates only – never diagnosis or clinical detail; all data stays in the client's jurisdiction.

## High-Level Requirements
E31 – High-Level Requirements
What the solution must achieve for this epic (MoSCoW prioritised, traced to standards and to the evidence of increments 1–5)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
HLR ID | Requirement | Rationale | Priority (MoSCoW) | Standards / sources | Applicable units | Review comment (sponsor / CMO / GRC) | Decision
E31-HLR-01 | Employees shall find wellbeing services they are eligible for in one catalogue in the employee app, with eligibility derived from HR / benefits data. | One front door; less confusion and higher uptake. | Should | ISO45003 | ALL – All subsidiaries & departments (group-wide)
E31-HLR-02 | Vendors shall be onboarded only with a DPA, a security due-diligence review and an approved integration contract. | Supplier risk and special-category data. | Must | ISO27001; LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E31-HLR-03 | Hand-off to a vendor shall require explicit consent and carry no OH clinical data; only aggregated participation and outcomes return. | Status-only and minimum-necessary principles. | Must | LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E31-HLR-04 | OH pathways may recommend marketplace services without disclosing why to the vendor. | Joins care and prevention safely. | Could | LOCAL-PDP | ALL – All subsidiaries & departments (group-wide)
E31-HLR-05 | Programme spend and outcomes shall be reported with suppression to support ROI decisions. | E12-F05 gap; value for money. | Should | ISO45001 | ALL – All subsidiaries & departments (group-wide)

## Feature List
E31 – Low-Level Feature List
Features that implement the high-level requirements, with roles, acceptance criteria and unit-specific notes
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Feature ID | Feature | Description | Primary roles | Priority (MoSCoW) | Traces to HLR | Acceptance criteria (summary) | Unit-specific notes | Review comment | Decision
E31-F01 | Marketplace catalogue | Catalogue with eligibility rules, search, accessibility and language support. | Employee; Health promotion lead | Should | E31-HLR-01 | Eligible services shown per employee; WCAG 2.2 AA. | Content reviewed by OH.
E31-F02 | Vendor onboarding workflow | Due-diligence checklist, DPA tracking, integration certification, periodic review. | Procurement; DPO; Cyber GRC | Must | E31-HLR-02 | No vendor live without DPA and review; annual re-review. | None
E31-F03 | Consented hand-off and aggregate return | Referral token / deep link with consent; aggregate participation and outcome import. | Employee; Vendor | Must | E31-HLR-03 | Consent recorded; vendor receives only identifier token and eligibility; aggregates suppressed. | None
E31-F04 | Pathway recommendations | OH clinicians or pathways suggest services; reason never shared. | OH nurse; Physician | Could | E31-HLR-04 | Recommendation visible to employee only; vendor sees no reason. | None
E31-F05 | Spend and outcome analytics | Spend, participation and outcome by programme with suppression. | Health promotion lead; Finance | Should | E31-HLR-05 | Quarterly report; suppression k ≥ 5. | Uses E26.

## Implementation Backlog
E31 – Implementation Backlog (line by line)
User stories, enablers, tasks and spikes with acceptance criteria, indicative estimates, horizon, priority, owner and dependencies
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Backlog ID | Feature ID | Feature (lookup) | Type | Title / user story | Acceptance criteria / definition of done | Story points (indicative) | Horizon | Priority | Owner / team | Dependencies (epics) | Sprint (to assign) | Status | Decision | Review comment
E31-BL-001 | E31-F02 |  | Task | Define the vendor due-diligence checklist, DPA template and integration certification | Approved by DPO, Cyber GRC and procurement | 3 | H3 | P1 | Procurement; Security & Privacy | E19 |  | Not started
E31-BL-002 | E31-F01 |  | Story | As an employee I want to browse wellbeing services I am eligible for in my language so that I can act on my health | Catalogue with eligibility; ar / en; accessible | 8 | H3 | P1 | Frontend / UX | E13, E21 |  | Not started
E31-BL-003 | E31-F01 |  | Enabler | Eligibility service from HR / benefits data (plan, subsidiary, role) | Eligibility cached with short TTL; no health data used | 5 | H3 | P1 | Integration | E15 |  | Not started
E31-BL-004 | E31-F03 |  | Story | As an employee I want to consent before I am handed to a vendor so that I control what they know | Explicit consent; token only; withdrawal supported | 5 | H3 | P1 | Frontend / UX; Platform / Backend | E16 |  | Not started
E31-BL-005 | E31-F03 |  | Enabler | Aggregate participation and outcome import from vendors bound to their organisation | org_scope-bound clients; aggregates only; suppression | 5 | H3 | P1 | Integration | E15 |  | Not started
E31-BL-006 | E31-F04 |  | Story | As an OH nurse I want to recommend a physiotherapy or sleep programme from the marketplace so that prevention follows the case | Recommendation to employee only; vendor sees no reason | 5 | H3 | P3 | Platform / Backend | E04 |  | Not started
E31-BL-007 | E31-F05 |  | Story | As the health promotion lead I want spend and outcome per programme so that I can decide what to renew | Quarterly suppressed report; finance definition | 5 | H3 | P2 | Data & Analytics | E26 |  | Not started
E31-BL-008 | E31-F02 |  | Task | Onboard the first three vendors (e.g. EAP, physiotherapy, sleep) through the workflow | Three vendors live with DPA and certification | 5 | H3 | P2 | Product Owner; Integration | – |  | Not started
E31-BL-009 | E31-F01 |  | Task | Content review process for marketplace listings by OH | Process approved; listings reviewed before publication | 2 | H3 | P2 | Clinical SME (OH Nurse / Physician) | – |  | Not started
E31-BL-010 | E31-F03 |  | Story | As a DPO I want a report of vendor hand-offs and consents so that I can evidence lawful sharing | Report by vendor; suppression | 3 | H3 | P2 | Platform / Backend | E16 |  | Not started
Total story points (indicative)
Items

## Legends
Legends – unit codes, standards, horizons, owners
Reference for codes used in this workbook
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Code | Meaning
ALL | All subsidiaries & departments (group-wide)
FLT | Flight Operations – pilots / flight crew
CAB | Cabin Services – cabin crew
GND | Ground Services – ramp, baggage, aircraft turnaround, GSE drivers
CGO | Cargo & Freight – warehouse, DGR/hazmat handling, cold chain, forklift
CAT | Catering – food production, food handlers, cold rooms, dish-wash, knives
ENG | Engineering & Maintenance – hangar, hazmat/chemicals, noise, heights, confined space
SEC | Security, Fire & Rescue, Medical Response
H1 | Horizon 1 – Go-live readiness and close the gaps (months 0–6)
H2 | Horizon 2 – Scale, intelligence and experience (months 6–18)
H3 | Horizon 3 – Ecosystem and industry-leading OH platform (months 18–36)
P1 / P2 / P3 | Backlog priority: P1 critical, P2 important, P3 desirable
ISO45001 | ISO 45001:2018 – OH&S management systems
ISO45003 | ISO 45003:2021 – psychological health & safety / psychosocial risk
ISO27001 | ISO/IEC 27001:2022 – information security management, Annex A
ISO27017 | ISO/IEC 27017 – information security controls for cloud services (tenant segregation)
ISO27701 | ISO/IEC 27701 – privacy information management
ISO22301 | ISO 22301 – business continuity management
ISO20889 | ISO/IEC 20889 – privacy-enhancing data de-identification techniques
ISO25012 | ISO/IEC 25012 – data quality model
ISO42001 | ISO/IEC 42001 – AI management system
ISO23894 | ISO/IEC 23894 – AI risk management
NIST-AI-RMF | NIST AI Risk Management Framework 1.0
EU-AI-ACT | Reg (EU) 2024/1689 (AI Act) – used as benchmark for risk classification, human oversight and transparency; local AI regulation applies
DCB0129 | DCB0129 / DCB0160 – clinical risk management for health IT manufacture and deployment (UK standards, used as benchmark)
SOC2 | AICPA Trust Services Criteria – CC (security), A (availability), C (confidentiality), PI, P
SRE | Site reliability engineering practice – service-level objectives, error budgets, burn-rate alerting
CIS-K8S | CIS Kubernetes / AKS benchmarks
NIST-SSDF | NIST SP 800-218 Secure Software Development Framework
SLSA | Supply-chain Levels for Software Artifacts – build provenance
OWASP-MASVS | OWASP Mobile Application Security Verification Standard v2
WCAG22 | W3C Web Content Accessibility Guidelines 2.2, level AA
EN301549 | EN 301 549 – accessibility requirements for ICT products and services
PDF-UA | ISO 14289 – accessible PDF
HL7-FHIR | HL7 FHIR R4 / R4B / R5 incl. subscriptions; SMART App Launch
HL7-ODH | HL7 FHIR Occupational Data for Health (ODH) IG
HL7-V2 | HL7 version 2.5.1 messaging (ORU, ORM, ADT)
IHE | IHE IT Infrastructure profiles – MHD, XDS.b, PIXm, PDQm, ATNA, IUA
SNOMED-ICD | SNOMED CT / ICD-10 or ICD-11 / LOINC – clinical, diagnosis and lab coding
EASA-MED | EASA Part-MED (Reg (EU) 1178/2011 Annex IV) – pilot medical certificates, cabin crew medical reports
ICAO-A1 | ICAO Annex 1 Ch. 6 – medical provisions for licensing
ICAO-A6 | ICAO Annex 6 – operator responsibilities incl. fatigue management (FRMS); ICAO Doc 9966 FRMS manual
ICAO-8984 | ICAO Doc 8984 – Manual of Civil Aviation Medicine
IOSA | IATA Operational Safety Audit – crew fitness and SMS standards
ILO-C161 | ILO Convention C161 – occupational health services
WHO-IHR | WHO International Health Regulations – preparedness and reporting
HIMSS | HIMSS Digital Health Indicator (incl. interoperability, person-enabled health, predictive analytics)
LOCAL-OHS | Local labour law, national OH&S regulation and civil aviation authority medical requirements (e.g. UK CAA, UAE GCAA)
LOCAL-PDP | Local personal-data-protection law + GDPR Art. 9 (special-category health data) as benchmark
Type: Story | User-facing functionality expressed as a user story
Type: Enabler | Architectural / technical foundation work
Type: Task | Non-development work (content, configuration, governance, training, procurement)
Type: Spike | Time-boxed investigation to remove uncertainty