## Catalogue
Epic catalogue E01–E31
All client epics, the security epic (renumbered E19) and the proposed strategy epics E20–E31 with status and evidence
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic | Name | Category | Status | Delivered by / horizon | Items traced | Implemented | Sign-off pending | Partial | Evidence, gaps and goal | Completion / delivery horizon | Team | Indicative SP | Workbook
E01 | Case Intake & Incident-Triggered Case Initiation | Business module | Done | Increment 1 | 42 | 26 | 0 | 16 | Module wz-e01-intake. Partial items: SMS / push channels, offline walk-in, export; triage and recordability content awaiting CMO / HSE sign-off. | H1 (sign-offs, E15 feeds) | T1 Clinical Care |  | Client workbook (scratchpad req*/)
E02 | Clinical Triage, Risk Stratification & Case Assignment | Business module | Done | Increment 1 | 32 | 26 | 0 | 6 | Module wz-e02-triage. 13 triage protocols DRAFT (CREW_FATIGUE and BODY_FLUID without red-flag question); SLA in elapsed minutes until the E18 business calendar exists. | H1 (sign-offs, E18 calendar) | T1 Clinical Care |  | Client workbook (scratchpad req*/)
E03 | Occupational Health Record & Clinical Encounter Documentation | Business module | Done | Increment 2 | 38 | 21 | 0 | 17 | Module wz-e03-record. Partial: OCR of image-only scans, device drivers, terminology server and licences, assistant provider (extension point only, no provider). | H1 sign-offs; H2 via E23 / E28 | T1 Clinical Care |  | Client workbook (scratchpad req*/)
E04 | Injury & Illness Management, Treatment Coordination & Partner Referrals | Business module | Done | Increment 4 | 33 | 24 | 0 | 9 | Module wz-e04-treatment. FHIR exchange tested with a simulated partner only; telehealth video not procured; e-prescribing no-op pending decision memo. | H1 (E15 connectors, D15, D19) | T1 Clinical Care |  | Client workbook (scratchpad req*/)
E05 | Fitness for Duty, Work Restrictions & Return-to-Work | Business module | Done | Increment 2 | 35 | 28 | 0 | 6 | Module wz-e05-fitness. 12 fitness standards and 28 of 150 job-demand profiles await validation; rostering transport not built; RTW training deferred. | H1 (sign-offs, rostering transport) | T1 Clinical Care |  | Client workbook (scratchpad req*/)
E06 | Absence & Sickness Management | Business module | Done | Increment 3 | 26 | 20 | 0 | 6 | Module wz-e06-absence. AbsenceFeedConnector is a no-op (push endpoint ready); HRIS / time & attendance / crew connectors outstanding. | H1 (E15 connectors) | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E07 | Medical Surveillance, Periodic & Statutory Medicals | Business module | Done | Increment 3 | 36 | 31 | 0 | 5 | Module wz-e07-surveillance. 13 programmes await CMO validation; CAA examination formats pending; bulk invitation not load-tested. | H1 sign-offs; H2 via E24 | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E08 | Workers' Compensation, Insurance & Claims Coordination | Business module | Done | Increment 4 | 24 | 19 | 0 | 5 | Module wz-e08-claims. Insurer / authority / ERP connectors default to outbox + content-free e-mail; report forms await Legal / HSE sign-off. | H1 (E15 connectors, sign-offs) | T1 Clinical Care |  | Client workbook (scratchpad req*/)
E09 | Mental Health, Psychosocial Risk & Peer Support Programmes | Business module | Done | Increment 5 | 27 | 21 | 5 | 1 | Module wz-e09-mentalhealth. Screening bands, urgent-risk protocol and signposting await sign-off; named-clinician seed (psych1) is a go-live item; EAP system API not connected. | H1 (sign-offs, go-live item) | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E10 | Drug, Alcohol & Psychoactive Substance Testing Programme | Business module | Done | Increment 5 | 20 | 14 | 3 | 3 | Module wz-e10-substance. Toxicology LIMS simulated (bound client ready); policy matrix PENDING; MRO document access via /documents outstanding (SEC-E05). | H1 (LIMS, MRO, sign-offs) | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E11 | Travel Health, Immunisation Campaigns & Communicable Disease / Exposure Management | Business module | Done | Increment 5 | 25 | 17 | 6 | 2 | Module wz-e11-travelhealth. Destination content source not licensed; protocol timers await sign-off; public-health authority submission by outbox + e-mail. | H1 (sign-offs, authority connector) | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E12 | Health Promotion, Wellbeing & Prevention Campaigns | Business module | Done | Increment 5 | 18 | 10 | 2 | 6 | Module wz-e12-promotion. Campaign app and wearable aggregator simulated; no ROI metric; absence not an insight source; hearing / vision results not captured in E12. | H1 connectors; H2 via E26 | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E13 | Employee & Manager Portal / App (self-service) | Platform | Partial | Increment 0, extended in 1–5 |  |  |  |  | Employee / crew portal as web, PWA and Capacitor shell; manager workspace; partner portal. Gaps: secure-storage and MAM plug-ins (R6), no offline, no native NFC, no push, Arabic only on employee screens. | H1 (store-ready) → E21 / E22 | T3 Experience & Mobile |  | Client catalogue (no workbook in repository)
E14 | Scheduling, Clinic Operations & Resource Management | Business module | Done | Increment 3 | 20 | 18 | 0 | 2 | Module wz-e14-scheduling. IoT cold-chain gateway and telehealth video not connected; campaign booking and capacity not load-tested. | H1 (D15, D16, load test) | T2 Workforce Health & Prevention |  | Client workbook (scratchpad req*/)
E15 | Integration & API Gateway | Platform | Partial | Increment 0, extended in 1–5 |  |  |  |  | Outbox, idempotency, FHIR R4 / HL7 v2 inbound, outbound allow-list. Gaps: production broker adapter (D3) and real connectors – HRIS, rostering, EHS transport, LIMS, insurer / TPA, authority, ERP, EAP, campaign app, wearables, public-health authority, SMS. | H1 (production grade) | T4 Integration & Interoperability |  | Client catalogue (no workbook in repository)
E16 | Identity, Access, Consent & Audit | Platform | Partial | Increment 0, extended in 1–5 |  |  |  |  | Multi-issuer OIDC, ABAC, consent, hash-chained audit, MFA gate, restricted classes. Gaps: MFA enrolment in PROD IdP, envelope encryption + re-encryption job (D5), audit anchoring (O2), automatic deletion of OH records (D6). | H1 (production grade) | T5 Platform & SRE |  | Client catalogue (no workbook in repository)
E17 | Analytics & Reporting (de-identified) | Platform | Partial | Increment 0, extended in 1–5 |  |  |  |  | De-identified view, KPI API with k = 5 suppression, per-module suppressed reports. Gaps: warehouse feed, read-only reporting role (O7), several client KPIs not computed (RTW within 5 days, documentation time, ROI, litigated-claim trend). | H1 completion → E26 | T6 Data & Analytics |  | Client catalogue (no workbook in repository)
E18 | Master Data & No-Code Configuration | Platform | Partial | Increment 0, extended in 1–5 |  |  |  |  | Versioned rules, protocols, templates and configuration API. Gaps: business / site calendar (O10), OH staff roster API or feed (O9), maker-checker for configuration changes, feature-flag governance (O34). | H1 (production grade) | T5 Platform & SRE |  | Client catalogue (no workbook in repository)
E19 | Security Hardening & Assurance (drafted as 'E15', renumbered) | Security | Planned | Drafted Oct 2026 (security assessment) |  |  |  |  | 17 HLRs, 17 features, 46 backlog items, 256 indicative SP (docs/security/epics). Go-live conditions G1–G6: pen test, scan evidence, AKS admission, demo-identity guard, CMK decision, patch SLAs. | H1 (Now / Next), H2 (Later) | T5 Platform & SRE | 256 | docs/security/epics/E15_Security_Hardening_and_Assurance.xlsx (to be renumbered E19)
E20 | Resilience & Tier-0 Operations (SRE) | Strategy (new) | Planned | Proposed – H1–H2 |  |  |  |  | Run PROD as a Tier-0 service at 99.99 % inside one jurisdiction, with failover, SLOs and drills proven, not assumed. | H1–H2 | T5 Platform & SRE | 107 | docs/strategy/epics/E20_Resilience_and_Tier0_Operations.xlsx
E21 | Accessibility & Internationalisation | Strategy (new) | Planned | Proposed – H1–H2 |  |  |  |  | WCAG 2.2 AA everywhere and full Arabic (RTL) plus the workforce's main languages across all apps and documents. | H1–H2 | T3 Experience & Mobile | 79 | docs/strategy/epics/E21_Accessibility_and_Internationalisation.xlsx
E22 | Native Mobile, Offline & Field Capability | Strategy (new) | Planned | Proposed – H1–H2 |  |  |  |  | A store- and MDM-ready crew and field app that works securely without network: offline first-aid capture, NFC, push and a certificate wallet. | H1–H2 | T3 Experience & Mobile | 75 | docs/strategy/epics/E22_Native_Mobile_and_Offline.xlsx
E23 | Interoperability Hub (FHIR, IHE, HL7 v2, national records) | Strategy (new) | Planned | Proposed – H1–H3 |  |  |  |  | Standards-based exchange with hospitals, labs, regulators and national health records – no more e-mail for clinical data. | H1–H3 | T4 Integration & Interoperability | 100 | docs/strategy/epics/E23_Interoperability_Hub.xlsx
E24 | Aviation Medical Certification & Regulator Interface | Strategy (new) | Planned | Proposed – H1–H2 |  |  |  |  | End-to-end AME certification with qualified signatures and electronic submission to the aviation authority's medical system. | H1–H2 | T1 Clinical Care | 63 | docs/strategy/epics/E24_Aviation_Medical_Certification_and_Regulator_Interface.xlsx
E25 | Fatigue Risk & Shift-Work Health (FRMS integration) | Strategy (new) | Planned | Proposed – H2 |  |  |  |  | Connect occupational health with the airline's FRMS and rostering – health-related fatigue handled clinically, insight shared only in aggregate. | H2 | T2 Workforce Health & Prevention | 47 | docs/strategy/epics/E25_Fatigue_Risk_and_Shift_Work_Health.xlsx
E26 | Data Platform & Research-Grade De-identified Datasets | Strategy (new) | Planned | Proposed – H1–H2 |  |  |  |  | An in-country, governed analytics platform that finally reports every client KPI and offers de-identified datasets safely. | H1–H2 | T6 Data & Analytics | 85 | docs/strategy/epics/E26_Data_Platform_and_Deidentified_Datasets.xlsx
E27 | Predictive Health & Absence Analytics (governed) | Strategy (new) | Planned | Proposed – H2–H3 |  |  |  |  | Advisory early-intervention signals for OH clinicians, under clinical-safety, bias and AI governance – never automated decisions. | H2–H3 | T6 Data & Analytics | 68 | docs/strategy/epics/E27_Predictive_Health_and_Absence_Analytics.xlsx
E28 | Clinical Documentation Assistant (governed) | Strategy (new) | Planned | Proposed – H1–H2 |  |  |  |  | Switch on the existing assistant extension point with an in-country, governed provider – drafts that clinicians always review and sign. | H1–H2 | T1 Clinical Care | 61 | docs/strategy/epics/E28_Clinical_Documentation_Assistant.xlsx
E29 | Multi-Subsidiary Tenancy, Onboarding & Extension Platform | Strategy (new) | Planned | Proposed – H2–H3 |  |  |  |  | Onboard a new subsidiary or client in weeks, with configurable tenancy, white-label branding and signed extensions instead of forks. | H2–H3 | T5 Platform & SRE | 81 | docs/strategy/epics/E29_Multi_Tenant_Subsidiary_Onboarding_and_Extensions.xlsx
E30 | Workforce Health Digital Twin & Capacity Planning | Strategy (new) | Planned | Proposed – H3 |  |  |  |  | An aggregate, de-identified model of workforce health readiness per base and fleet, for scenario planning and OH capacity. | H3 | T6 Data & Analytics | 59 | docs/strategy/epics/E30_Workforce_Health_Digital_Twin_and_Capacity_Planning.xlsx
E31 | Employee Wellbeing Marketplace & Benefits Integration | Strategy (new) | Planned | Proposed – H3 |  |  |  |  | A curated, integration-led marketplace of wellbeing services in the employee app – eligibility from benefits systems, no OH data to vendors. | H3 | T2 Workforce Health & Prevention | 46 | docs/strategy/epics/E31_Wellbeing_Marketplace_and_Benefits_Integration.xlsx
Done
Partial
Planned
Items traced (E01–E14)
Implemented
Implemented – sign-off pending
Partial
Indicative SP – E19 to E31
Sources: release notes and requirements traceability matrices of increments 1–5 (per-epic counts; increment 5 distinguishes 'implemented – configuration needs sign-off'); architecture document 01 Sections 1, 16–18; Security Enhancement Guideline. E05 also has one deferred training item. 'Done' means functionally delivered and verified – go-live still depends on the sign-offs and connectors listed.

## Horizon roadmap
Horizon roadmap – 36 months from November 2026
H1 go-live readiness (Q1–Q2) · H2 scale, intelligence and experience (Q3–Q6) · H3 ecosystem and industry leadership (Q7–Q12). Shaded = active.
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
ID | Work item | Team / owner | Q1 Nov–Jan 27 | Q2 Feb–Apr 27 | Q3 May–Jul 27 | Q4 Aug–Oct 27 | Q5 Nov–Jan 28 | Q6 Feb–Apr 28 | Q7 May–Jul 28 | Q8 Aug–Oct 28 | Q9 Nov–Jan 29 | Q10 Feb–Apr 29 | Q11 May–Jul 29 | Q12 Aug–Oct 29 | Milestone / exit criterion
GL-01 | Clinical, MRO and legal sign-offs (O11, O14, O19, O31; RTM-5 follow-up register) | CMO, MRO, Legal, DPO | ■ | ■ | [10 empty] | Go-live gate
GL-02 | Go-live configuration items (named clinicians O38, MFA enrolment O23 / O32, GitHub Environments O33) | Platform operations, IAM | ■ | [11 empty] | Go-live gate
GL-03 | Independent penetration test and retest (SEC-E01) – go-live condition G1 | CISO office |  | ■ | [10 empty] | Go-live gate
GL-04 | Tier-0 two-region Azure landing zone and PROD go-live (16-week plan in the decision pack) | Platform & SRE | ■ | ■ | [10 empty] | Go-live gate
GL-05 | Retention classes approved and purge jobs enabled (D6, O12, O22, O27, O36) | DPO, Legal | ■ | ■ | [10 empty] | Go-live gate
E13 | Employee & Manager Portal / App (self-service) – complete to production grade | T3 Experience & Mobile | ■ | ■ | [10 empty] | Store / MDM-ready app
E15 | Integration & API Gateway – complete to production grade | T4 Integration & Interoperability | ■ | ■ | ■ | [9 empty] | 12 production connectors live
E16 | Identity, Access, Consent & Audit – complete to production grade | T5 Platform & SRE | ■ | ■ | [10 empty] | Envelope encryption, anchoring, purge jobs
E17 | Analytics & Reporting (de-identified) – complete to production grade | T6 Data & Analytics | ■ | ■ | [10 empty] | Outstanding KPIs on KPI API
E18 | Master Data & No-Code Configuration – complete to production grade | T5 Platform & SRE | ■ | ■ | [10 empty] | Calendar, roster feed, maker-checker
E19 | Security Hardening & Assurance (drafted as 'E15', renumbered) | T5 Platform & SRE + security champions | ■ | ■ | ■ | ■ | [8 empty] | G1–G6 met; Later items closed
E20 | Resilience & Tier-0 Operations (SRE) | T5 Platform & SRE | ■ | ■ | ■ | ■ | [8 empty] | Failover drill RTO ≤ 15 min proven
E21 | Accessibility & Internationalisation | T3 Experience & Mobile |  | ■ | ■ | ■ | ■ | [7 empty] | WCAG 2.2 AA audit clean; Arabic everywhere
E22 | Native Mobile, Offline & Field Capability | T3 Experience & Mobile | ■ | ■ | ■ | ■ | ■ | [7 empty] | Offline capture live at airside posts
E23 | Interoperability Hub (FHIR, IHE, HL7 v2, national records) | T4 Integration & Interoperability |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  | First live FHIR hospital + v2 lab
E24 | Aviation Medical Certification & Regulator Interface | T1 Clinical Care |  | ■ | ■ | ■ | ■ | ■ | [6 empty] | Electronic submission to the first authority
E25 | Fatigue Risk & Shift-Work Health (FRMS integration) | T2 Workforce Health & Prevention |  |  |  | ■ | ■ | ■ | ■ | [5 empty] | FRMS referral and roster restriction codes live
E26 | Data Platform & Research-Grade De-identified Datasets | T6 Data & Analytics |  | ■ | ■ | ■ | ■ | ■ | [6 empty] | All client KPIs from one semantic layer
E27 | Predictive Health & Absence Analytics (governed) | T6 Data & Analytics |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ |  |  | Silent pilot passes safety case → live pilot
E28 | Clinical Documentation Assistant (governed) | T1 Clinical Care |  | ■ | ■ | ■ | ■ | ■ | ■ | [5 empty] | 5-clinician pilot → staged roll-out
E29 | Multi-Subsidiary Tenancy, Onboarding & Extension Platform | T5 Platform & SRE |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  | Subsidiary onboarded in ≤ 4 weeks
E30 | Workforce Health Digital Twin & Capacity Planning | T6 Data & Analytics | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | Readiness dashboard and scenarios
E31 | Employee Wellbeing Marketplace & Benefits Integration | T2 Workforce Health & Prevention | [7 empty] | ■ | ■ | ■ | ■ | ■ | Three vendors live with DPA

## Dependencies
Dependencies between epics
Predecessor → successor, hard (blocks start or go-live) or soft (reduces value or adds rework)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Predecessor | Successor | Type | Reason | Predecessor status | Successor horizon
E15 | E06 | Hard | Absence feed connectors (HRIS, T&A, crew) – AbsenceFeedConnector is a no-op today | Partial | Done – completion H1
E15 | E05 | Hard | Rostering transport for the status-only fitness feed (O15) | Partial | Done – completion H1
E15 | E10 | Hard | Toxicology LIMS onboarding as bound integration client (O30) | Partial | Done – completion H1
E15 | E08 | Hard | Insurer FNOL, authority e-reporting and ERP connectors (D18, O24) | Partial | Done – completion H1
E15 | E12 | Soft | Campaign app and wearable aggregator (E12-F04 partial) | Partial | Done – completion H1
E15 | E11 | Hard | Public-health authority submission (default outbox + e-mail) | Partial | Done – completion H1
E16 | E20 | Hard | Customer-managed keys and envelope encryption before the PROD server and replica exist (SEC-E09, D5) | Partial | H1–H2
E19 | E20 | Hard | Signed-image admission and private control plane for the PROD clusters (SEC-E03, SEC-E04) | Planned | H1–H2
E20 | Go-live | Hard | Two-region topology and first DR drill are Tier-0 go-live conditions | Planned | H1
E19 | Go-live | Hard | Go-live conditions G1–G6 (pen test, scan evidence, admission, demo-identity guard, CMK, patch SLAs) | Planned | H1
E13 | E22 | Hard | Native mobile builds on the Capacitor shell and the employee app | Partial | H1–H2
E19 | E22 | Hard | Mobile hardening and MASVS assessment (SEC-E11) | Planned | H1–H2
E18 | E21 | Soft | Languages, templates and station list in master data | Partial | H1–H2
E22 | E21 | Soft | Platform accessibility APIs in the native app | Planned | H1–H2
E15 | E23 | Hard | Gateway, broker adapter and outbox are the transport of the hub | Partial | H1–H3
E18 | E23 | Soft | Terminology registry and value sets | Partial | H1–H3
E05 | E24 | Hard | Crew assessment and status-only roster feed | Done | H1–H2
E07 | E24 | Hard | Crew medical certificates and validity | Done | H1–H2
E23 | E24 | Soft | Document exchange and FHIR profiles for authority interfaces offering APIs | Planned | H1–H2
E15 | E25 | Hard | FRMS and rostering transport | Partial | H2
E26 | E25 | Soft | Aggregated fatigue indicators via the data platform | Planned | H2
E17 | E26 | Hard | De-identified view, KPI API and suppression are the starting point | Partial | H1–H2
E15 | E26 | Hard | CDC / broker feed into the analytics store | Partial | H1–H2
E20 | E26 | Soft | In-country analytics store in the approved region pair | Planned | H1–H2
E26 | E27 | Hard | No model without the governed, pseudonymised data platform | Planned | H2–H3
E06 | E27 | Hard | Early-intervention queue is where signals appear | Done | H2–H3
E27 | E28 | Soft | Shared AI governance board and clinical safety process | Planned | H1–H2
E03 | E28 | Hard | AiDocumentationProvider extension point, consent purpose and audit | Done | H1–H2
E21 | E28 | Soft | Arabic language support | Planned | H1–H2
E18 | E29 | Hard | Tenant configuration and content packs | Partial | H2–H3
E20 | E29 | Hard | Instances, overlays and upgrade orchestration | Planned | H2–H3
E19 | E29 | Hard | Extension signing and tenant isolation in the pen-test scope | Planned | H2–H3
E26 | E30 | Hard | Aggregated readiness data | Planned | H3
E27 | E30 | Soft | Demand forecasts | Planned | H3
E14 | E30 | Hard | Clinic capacity model | Done | H3
E12 | E31 | Hard | Campaign app, wearable and participation patterns | Done | H3
E26 | E31 | Soft | Spend and outcome analytics (ROI) | Planned | H3

## Capacity plan
Capacity plan – indicative team-sprints (not prices)
Velocity 30 SP per team per two-week sprint; planning allowance ×1.5 / ×2.0 / ×2.5 for H1 / H2 / H3 epics (refinement, non-functional work, defects); 6 product teams in H1, 5 in H2, 4 in H3; 35 % of capacity reserved for run, defects and sign-off support
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Epic | Name | Team | Horizon | Indicative SP | Planning team-sprints | Quarters | Q1 Nov–Jan 27 | Q2 Feb–Apr 27 | Q3 May–Jul 27 | Q4 Aug–Oct 27 | Q5 Nov–Jan 28 | Q6 Feb–Apr 28 | Q7 May–Jul 28 | Q8 Aug–Oct 28 | Q9 Nov–Jan 29 | Q10 Feb–Apr 29 | Q11 May–Jul 29 | Q12 Aug–Oct 29
E13 | Store-ready mobile build (secure storage, MAM SDK registration), status-only screens for crew scheduling and hygiene manager, per-user channel preferences | T3 Experience & Mobile | H1 |  | 4 | 1–2
E15 | Broker adapter (D3) and 12 production connectors: HRIS, rostering / duty feed, EHS transport, LIMS, insurer / TPA FNOL, authority e-reporting, ERP, EAP, campaign app, wearable aggregator, public-health authority, SMS gateway | T4 Integration & Interoperability | H1 |  | 22 | 1–3
E16 | MFA enrolment evidence, envelope encryption + re-encryption job, audit hash anchoring and SIEM export, retention purge jobs for OH records after DPO approval | T5 Platform & SRE | H1 |  | 7 | 1–2
E17 | Read-only reporting role, outstanding client KPIs on the current KPI API, warehouse feed groundwork shared with E26 | T6 Data & Analytics | H1 |  | 4 | 1–2
E18 | Business / site calendar, OH staff roster feed, maker-checker on configuration changes, feature-flag governance | T5 Platform & SRE | H1 |  | 5 | 1–2
E19 | Security Hardening & Assurance – 46 backlog items, 256 indicative SP (Now / Next in H1, Later in H2) | T5 Platform & SRE + security champions | H1–H2 | 256 | 9 | 1–4
E20 | Resilience & Tier-0 Operations (SRE) | T5 Platform & SRE | H1–H2 | 107 |  | 1–4
E21 | Accessibility & Internationalisation | T3 Experience & Mobile | H1–H2 | 79 |  | 2–5
E22 | Native Mobile, Offline & Field Capability | T3 Experience & Mobile | H1–H2 | 75 |  | 1–5
E23 | Interoperability Hub (FHIR, IHE, HL7 v2, national records) | T4 Integration & Interoperability | H1–H3 | 100 |  | 2–8
E24 | Aviation Medical Certification & Regulator Interface | T1 Clinical Care | H1–H2 | 63 |  | 2–6
E25 | Fatigue Risk & Shift-Work Health (FRMS integration) | T2 Workforce Health & Prevention | H2 | 47 |  | 4–7
E26 | Data Platform & Research-Grade De-identified Datasets | T6 Data & Analytics | H1–H2 | 85 |  | 2–6
E27 | Predictive Health & Absence Analytics (governed) | T6 Data & Analytics | H2–H3 | 68 |  | 5–10
E28 | Clinical Documentation Assistant (governed) | T1 Clinical Care | H1–H2 | 61 |  | 2–7
E29 | Multi-Subsidiary Tenancy, Onboarding & Extension Platform | T5 Platform & SRE | H2–H3 | 81 |  | 4–10
E30 | Workforce Health Digital Twin & Capacity Planning | T6 Data & Analytics | H3 | 59 |  | 7–12
E31 | Employee Wellbeing Marketplace & Benefits Integration | T2 Workforce Health & Prevention | H3 | 46 |  | 8–12
EVO | Evolution of delivered modules E01–E14 (feedback, sign-off changes, regulatory change) | T1 / T2 | H2–H3 |  | 40 | 3–12
Demand – roadmap team-sprints
| Funded product teams | [5 empty] | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4
Capacity – gross team-sprints
Capacity – available for roadmap
Headroom for options (E32+) or client demand
Utilisation of available capacity
| T1 Clinical Care | E01–E05, E08, E24, E28 – Product owner (OH), clinical safety officer liaison, 5–6 engineers, QA
| T2 Workforce Health & Prevention | E06, E07, E09–E12, E14, E25, E31 – Product owner (prevention), 5–6 engineers, QA
| T3 Experience & Mobile | E13, E21, E22 – Product owner (experience), UX / accessibility lead, web + mobile engineers
| T4 Integration & Interoperability | E15, E23 – Integration architect, 4–5 engineers, interface analyst
| T5 Platform & SRE | E16, E18, E19, E20, E29 – Platform lead, SREs, security champion, DBA
| T6 Data & Analytics | E17, E26, E27, E30 – Data product owner, data engineers, data scientist, privacy engineer
Reading the plan: utilisation above 100 % (red) means the quarter needs more capacity or a later start. H1 is the constrained horizon because the platform epics, E19 security and the Tier-0 build all land before go-live – decision S5 asks for a temporary integration capacity uplift in Q1–Q3. H2 and H3 epics carry a larger uncertainty allowance (×2.0 / ×2.5) because their backlogs are first cuts; the remaining headroom is deliberately unallocated for option epics (E32+), client demand and estimate overruns, and is reviewed at each horizon gate. Team-sprints are indicative and exclude business sign-off effort, external penetration testing, licences and hosting.

## KPI tree
KPI tree – north star, outcomes and drivers
Targets are indicative and taken from the client epic KPIs where available; baselines must be measured in the first 90 days of operation
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Strategy beyond increment 5, draft for C-suite, CIO, CMO / Nursing Head and Cyber GRC review ¦ 30 October 2026
Level | ID | Parent | KPI | Target (indicative) | Owner | Epics | Baseline
North star | NS |  | Every safety-critical employee fit, supported and back at work safely – with health data that never leaks | – | CMO + CIO | All | to measure
Outcome | O1 | NS | Lost workdays per lost-time case | −25 % in 12 months (E05 KPI; illustrative business case) | CMO / Nursing Head | E05, E06, E27 | to measure
Outcome | O2 | NS | Lost-time claim cost per case | −15 % in 18 months (E08 KPI; illustrative) | Claims lead / Finance | E04, E08, E26 | to measure
Outcome | O3 | NS | Crew medical certificate lapses | 0 (E07 KPI) | AME lead / Crew licensing | E07, E24, E30 | to measure
Outcome | O4 | NS | Platform availability (PROD, measured SLO) | ≥ 99.99 % per month | CIO / Head of SRE | E19, E20 | to measure
Outcome | O5 | NS | Disclosure or residency incidents involving health data | 0 | DPO / CISO | E16, E19, E26, E29 | to measure
Outcome | O6 | NS | Employee trust and reach | ≥ 90 % awareness of confidential pathways; app adoption ≥ 70 % of crew | Nursing Head / HR | E09, E13, E21, E22 | to measure
Driver | D1.1 | O1 | % long-term absences (> 4 weeks) with an OH case | ≥ 95 % (E06 KPI) | Nursing Head | E06, E15 | to measure
Driver | D1.2 | O1 | % RTW plans started within 5 days of fitness decision | ≥ 90 % (E05 KPI) | Nursing Head | E05, E17 | to measure
Driver | D1.3 | O1 | Early-intervention contacts generated by governed risk signals and accepted by clinicians | ≥ 70 % rated useful in pilot | CMO | E27 | to measure
Driver | D2.1 | O2 | FROI / statutory submissions within deadline | 100 % (E08 KPI) | Claims lead | E08, E15 | to measure
Driver | D2.2 | O2 | Median referral-to-appointment time | < 5 working days (E04 KPI) | Case management | E04, E23 | to measure
Driver | D3.1 | O3 | Regulator submissions within the authority's deadline | ≥ 98 % | AME lead | E24 | to measure
Driver | D3.2 | O3 | Fitness status reaching rostering within 15 minutes | 100 % (E05 KPI) | Crew scheduling | E05, E15, E25 | to measure
Driver | D4.1 | O4 | Region failover proven in drill (RTO / RPO) | ≤ 15 min / ≤ 5 min, every quarter | Head of SRE | E20 | to measure
Driver | D4.2 | O4 | Change failure rate | ≤ 10 % | Engineering leads | E20, E19 | to measure
Driver | D5.1 | O5 | Critical / High vulnerabilities open beyond SLA | 0 | CISO | E19 | to measure
Driver | D5.2 | O5 | Re-identification incidents from analytics or research datasets | 0 | DPO | E26, E27 | to measure
Driver | D6.1 | O6 | WCAG 2.2 AA critical / serious issues open | 0 across the four web apps and the mobile app | Head of Experience | E21 | to measure
Driver | D6.2 | O6 | Employee-facing screens available in Arabic (RTL) and top workforce languages | 100 % Arabic; ≥ 95 % top-5 languages | Head of Experience | E21 | to measure
Driver | D6.3 | O6 | Documentation time per encounter (frees clinician time for people) | −30 % vs baseline (E03 KPI) | CMO | E03, E28 | to measure