## Remaining epics
Remaining epics – how many are left
13 done · 5 partial (E13, E15–E18) · 13 planned (E19–E31) → 18 epics with work remaining, 13 not started
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Remaining Epics Build Plan, developer-facing ¦ 30 October 2026 ¦ effort indicative
Counts
Status | Epics | Count
Done | E01, E02, E03, E04, E05, E06, E07, E08, E09, E10, E11, E12, E14 | 13
Partial (platform, completed to production grade in H1) | E13, E15, E16, E17, E18 | 5
Planned – security (drafted as "E15" in docs/security/epics/, renumbered E19 – decision S2) | E19 | 1
Planned – strategy epics | E20, E21, E22, E23, E24, E25, E26, E27, E28, E29, E30, E31 | 12
Total |  | 31
Work remaining (partial + planned) |  | 18
Not started (planned) |  | 13
Remaining epics (indicative SP and team-sprints from the Capacity plan)
Epic | Name | Status | Team | Horizon | Quarters | Indicative SP | Team-sprints | Where the code lands | Exit criterion (roadmap)
E13 | Employee & Manager Portal / App – completion | Partial | T3 | H1 | Q1–Q2 | – | 4 | web/employee-app (Capacitor, secure storage, MAM), web/manager-workspace status-only screens | Store / MDM-ready app
E15 | Integration & API Gateway – completion | Partial | T4 | H1 | Q1–Q3 | – | 22 | platform/wz-integration (EventPublisher broker adapter, connectors), consumer adapters in E05, E06, E08, E10, E11, E12 | 12 production connectors live
E16 | Identity, Access, Consent & Audit – completion | Partial | T5 | H1 | Q1–Q2 | – | 7 | platform/wz-secrets (envelope encryption), platform/wz-security (audit anchoring, SIEM export), platform/wz-documents (RetentionService purge) | Envelope encryption, anchoring, purge jobs
E17 | Analytics & Reporting – completion | Partial | T6 | H1 | Q1–Q2 | – | 4 | platform/wz-analytics (KpiService), read-only reporting role (Flyway grants) | Outstanding KPIs on the KPI API
E18 | Master Data & No-Code Configuration – completion | Partial | T5 | H1 | Q1–Q2 | – | 5 | platform/wz-masterdata (calendar, staff roster feed, maker-checker on ConfigService, flag register) | Calendar, roster feed, maker-checker
E19 | Security Hardening & Assurance | Planned | T5 + champions | H1–H2 | Q1–Q4 | 256 | 9 | Platform, CI, Terraform, Helm – no new module | G1–G6 met; Later items closed
E20 | Resilience & Tier-0 Operations (SRE) | Planned | T5 | H1–H2 | Q1–Q4 | 107 | 6 | deploy/terraform, deploy/helm, .github/workflows, load tests – no new module | Failover drill RTO ≤ 15 min proven
E21 | Accessibility & Internationalisation | Planned | T3 | H1–H2 | Q2–Q5 | 79 | 4 | Four web apps, PdfRenderer, ClinicalTextDetector, master data – no new module | WCAG 2.2 AA audit clean; Arabic everywhere
E22 | Native Mobile, Offline & Field Capability | Planned | T3 | H1–H2 | Q1–Q5 | 75 | 4 | modules/wz-e22-field + web/employee-app | Offline capture live at airside posts
E23 | Interoperability Hub | Planned | T4 | H1–H3 | Q2–Q8 | 100 | 7 | modules/wz-e23-interop + platform/wz-integration (fhir, hl7, terminology) | First live FHIR hospital + v2 laboratory
E24 | Aviation Medical Certification & Regulator Interface | Planned | T1 | H1–H2 | Q2–Q6 | 63 | 5 | modules/wz-e24-aeromedical | Electronic submission to the first authority
E25 | Fatigue Risk & Shift-Work Health | Planned | T2 | H2 | Q4–Q7 | 47 | 4 | modules/wz-e25-fatigue | FRMS referral and roster restriction codes live
E26 | Data Platform & De-identified Datasets | Planned | T6 | H1–H2 | Q2–Q6 | 85 | 5 | modules/wz-e26-dataplatform + platform/wz-analytics + pipeline infrastructure | All client KPIs from one semantic layer
E27 | Predictive Health & Absence Analytics | Planned | T6 | H2–H3 | Q5–Q10 | 68 | 5 | modules/wz-e27-predictive + in-country training / scoring in the data platform | Silent pilot passes safety case → live pilot
E28 | Clinical Documentation Assistant | Planned | T1 | H1–H2 | Q2–Q7 | 61 | 5 | modules/wz-e28-docassist (implements the E03 AiDocumentationProvider) | 5-clinician pilot → staged roll-out
E29 | Multi-Subsidiary Tenancy, Onboarding & Extensions | Planned | T5 | H2–H3 | Q4–Q10 | 81 | 6 | modules/wz-e29-tenancy + launcher change in apps/wz-core-app + flag register in wz-masterdata | Subsidiary onboarded in ≤ 4 weeks
E30 | Workforce Health Digital Twin & Capacity Planning | Planned | T6 | H3 | Q7–Q12 | 59 | 5 | modules/wz-e30-readiness | Readiness dashboard and scenarios
E31 | Wellbeing Marketplace & Benefits Integration | Planned | T2 | H3 | Q8–Q12 | 46 | 4 | modules/wz-e31-marketplace | Three vendors live with DPA
| Total |  |  |  |  | 1127 | 111
Team-sprints: velocity 30 SP per team-sprint, allowance ×1.5 / ×2.0 / ×2.5 for H1 / H2 / H3 epics; platform completion (E13, E15–E18) estimated in team-sprints only. Quarters: Q1 = Nov 2026–Jan 2027 … Q12 = Aug–Oct 2029. Effort is indicative.

## Dependency matrix
Dependency matrix – remaining epic × prerequisite
H hard · S soft (catalogue Dependencies sheet) · W named in the epic workbook · ● before code generation · ◐ simulated default now, needed before go-live · ○ soft / value
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Remaining Epics Build Plan, developer-facing ¦ 30 October 2026 ¦ effort indicative
A · Epic × epic (rows = remaining epic, columns = predecessor)
Epic ↓ / needs → | E13 | E15 | E16 | E17 | E18 | E19 | E20 | E21 | E22 | E23 | E26 | E27 | Delivered modules it builds on
E13 | [12 empty] | E01 (self-referral)
E15 | [12 empty] | E05, E06, E08, E10, E11, E12 (consumer adapters)
E16 | [12 empty] | – | bar: E19
E17 | [12 empty] | –
E18 | [12 empty] | –
E19 | [12 empty] | E09, E10 (restricted documents)
E20 | [12 empty] | E05 (manual fallback) | bar: E15 to E16; E18 to E19
E21 | [12 empty] | E03, E09 (clinical translations) | bar: E13 to E16; E18; E22
E22 | [12 empty] | E01, E02, E07, E11 | bar: E13 to E16; E19
E23 | E15: H; E16: W; E18: S | E03, E04
E24 | [12 empty] | E05 (H), E07 (H), E03 | bar: E15 to E16; E18; E23
E25 | E13: W; E15: H; E16: W; E21: W; E26: S | E02, E05, E09, E12
E26 | E15: H; E16: W; E17: H; E18: W; E19: W; E20: S | E06, E12
E27 | [12 empty] | E06 (H), E05, E12 | bar: E16; E19 to E20; E26
E28 | [12 empty] | E03 (H) | bar: E16; E19; E21; E26 to E27
E29 | [12 empty] | – | bar: E16; E18 to E21
E30 | E15: W; E26: H; E27: S | E14 (H), E07, E11, E24 (W)
E31 | [12 empty] | E12 (H), E04 | bar: E13 to E16; E19; E21; E26
B · Epic × external (X), decision / sign-off (DS) and environment (N) prerequisites
Epic | X1 Partner APIs | X2 Terminology | X3 Authority | X4 Trust service | X5 MDM / stores / push | X6 In-country assistant | X7 FRMS | X8 HIE | X9 Benefits / vendors | X10 Instruments | X11 Independent assessor | DS1 CSO | DS2 AI board | DS3 DPIA | DS4 PMO | DS5 ADR | DS6 Sign-off | N1 Tier-0 | N2 Analytics store | N3 Prod-like UAT | N4 Device lab
E13 | [15 empty] | ● D4 |  | ◐ |  |  | ● | bar: E18
E15 | [13 empty] | ● |  | ● D3 | ◐ | ◐ |  | ◐ | bar: E13
E16 | [15 empty] | ● D5 | ◐ G10 | ●
E17 | [16 empty] | ● KPI defs | ◐
E18 | E13: ◐ roster | [5 empty] | ◐
E19 | [14 empty] | ● | ● D5 |  | ● |  | ● | bar: E26
E20 | [14 empty] | ● | ● D1 / D9 | ● DS8 | ● |  | ●
E21 | E23: ◐; E26: ◐ WCAG |  |  | ● |  | ◐ | ◐ |  |  | ●
E22 | E13: ◐ HRIS; E18: ●; E26: ◐ MASVS; E27: ○ |  | ● | ● | ● D4 | ● dataset | ◐ |  |  | ●
E23 | E13: ◐; E15: ●; E21: ◐ H3 |  | ● | ● | ● D10 |  | ◐
E24 | E16: ● spike; E17: ●; E27: ● |  | ● | ● | ● D12 | ◐ templates | ◐
E25 | [13 empty] | ● | ● |  | ● CREW_FATIGUE | ◐ | ○ | bar: E13; E20; E23; E27
E26 | [13 empty] | ● | ● | ● D5 keys | ● de-id std | ◐ | ●
E27 | [12 empty] | ● | ● | ● |  | ● safety case | ◐ | ● | bar: E27
E28 | [12 empty] | ● | ● | ● | ● D13 | ● safety case | ◐ | bar: E19; E27
E29 | E26: ◐ pen test |  | ● | ● | ● D22, S8 |  | ● |  | ●
E30 | E13: ◐ roster / network | ○ | ● | ● |  |  | ◐ | ●
E31 | [13 empty] | ● | ● |  | ● content review | ◐ | ○ | bar: E22
C · Cross-cutting technical prerequisites in the code base (TP-01 … TP-12)
# | E13: Prerequisite; E15: Today (verified); E16: Change
TP-01 | E13: Module catalogue; E15: ModuleRegistry.CATALOGUE lists E01–E18 only; a CaseModule bean switches an entry to IMPLEMENTED; E16: Add catalogue entries E19–E31 (PLANNED, group platform / strategy) so that GET /api/v1/modules and modules.eNN.enabled work for the new codes; planned modules default to disabled
TP-02 | E13: Schema list; E15: spring.flyway.schemas in apps/wz-core-app/src/main/resources/application.yml and migrations.job.core.schemas in deploy/helm/wellnessz/values.yaml list 18 schemas ending with promotion; E16: Each new schema in the five places of CI/CD Guide 10.1 step 3: application.yml, Helm values, deploy/local/postgres/01-init-wellnessz.sh, deploy/sql/bootstrap-managed-postgres.sql, deploy/hybrid/cnpg/03-cluster.yaml
TP-03 | E13: Flyway ordering; E15: V1–V20 applied; no outOfOrder setting anywhere in apps/ or deploy/ → strict ordering; E16: Next free number is V21. Keep one reservation register (Section 6.1); a lower number must never merge after a higher one has been applied in DEV
TP-04 | E13: ArchUnit; E15: ArchitectureTest has 22 rules; new packages must be added to platformDoesNotDependOnBusinessModules, kernelDoesNotDependOnBusinessModules, documentServiceIsAPlatformService and earlierModulesDoNotDependOnLaterOnes; E16: One rule per new module (Section 6.3) plus deliveredModulesDoNotDependOnStrategyModules and restrictedClassesStayOutOfStrategyModules (proposed)
TP-05 | E13: BFF allow-list; E15: ApiProxyController.CORE_WORKSPACE_RESOURCES (13 workspace paths after increment 5); everything else under /api/v1/** is proxied as is; E16: Add a path only when a module exposes /api/v1/workspace/... for manager / HR roles; extend ApiProxyPathTest
TP-06 | E13: Consent purposes; E15: ConsentPurpose has 8 values incl. AI_DOCUMENTATION, RESEARCH_DEIDENTIFIED, WEARABLE_DATA; E16: Add FRMS_REFERRAL (E25), MARKETPLACE_HANDOFF (E31), HIE_EXCHANGE (E23) (proposed) – each needs DPO wording
TP-07 | E13: Case sources; E15: CaseSource has 12 values (no FRMS); E16: Add FRMS_REFERRAL (E25) (proposed); check the matching check constraint in the case schema in the same migration
TP-08 | E13: Connector catalogue; E15: ConnectorRegistry lists 10 connector descriptors; E16: Add descriptors for broker destinations and new partners (authority gateway, FRMS, HIE, push provider, benefits / vendors) and their DPO-approved field lists (OutboundPayloadGuard)
TP-09 | E13: Idempotent machine and mobile writes; E15: IdempotencyService exists in wz-integration but no business module uses it; EncounterController (E01) has plain @PostMapping; E16: E22 offline sync needs Idempotency-Key on E01 encounter creation and E02 telephone triage (EVO change to E01 / E02)
TP-10 | E13: Feature flags; E15: WZ_FEATURE_* is plumbing only; no product feature reads a flag (Customisation Guide 5.2); E16: One flag register in wz-masterdata (E18) extended by E20 (owner, expiry, audit) and E29 (tenant scope) – build it once (Section 6.5)
TP-11 | E13: Roles; E15: 38 canonical roles in com.wellnessz.common.model.Roles; E16: New roles in Roles, realm JSON, scope mappings of wellnessz-bff / wellnessz-mobile, Entra app roles; external roles in wellnessz.security.mfa-required-roles and MfaRoleGateTest
TP-12 | E13: E2E and documents; E15: tools/e2e/e2e-increment1.js … e2e-increment5.js; 121 checks; E16: Continue the increment numbering: Wave 1 = increment 6, Wave 2 = increment 7, Wave 3 = increment 8, Wave 4 = increments 9–11 (docs/increment-06/ …, docs/images/screens/increment-06/ …)
D · Per-epic technical prerequisites (modules, SPIs, schema, Flyway, ArchUnit, BFF, web)
Epic | E13: Builds on (existing modules – Maven dependency); E15: Existing SPIs / services consumed (verified); E16: SPIs implemented or added; E17: Schema · first Flyway (indicative); E18: ArchUnit; E19: BFF; E20: Web
E13 | E13: E01 (self-referral), kernel CaseService.selfReferral; E15: managedConfig.ts / runtimeConfig.ts (MDM keys), statusOnly.ts whitelist; E16: –; E17: none; E18: –; E19: –; E20: employee-app (Capacitor plug-ins), manager-workspace (crew scheduling, hygiene manager status-only screens)
E15 | E13: platform only; E15: EventPublisher (outbox delivery SPI), OutboxRelay, ConnectorRegistry, InboundService, IdempotencyService, JobRunGuard; module SPIs AbsenceFeedConnector (E06), ClaimsSubmissionGateway (E08), CrewStatusEnricher (E02), NotificationChannel (SMS); E16: Broker adapter implementing EventPublisher; real beans behind the module SPIs; E17: connector state if needed · V24; E18: none new; E19: –; E20: –
E16 | E13: platform only; E15: MasterKey, FieldEncryptor (wellnessz.crypto.active-key-version), AuditService, RetentionService; E16: KMS-wrapped data keys (proposed KeyWrappingProvider), re-encryption job, audit anchor, purge jobs; E17: platform / docs tables · V22; E18: none new; E19: –; E20: –
E17 | E13: platform only; E15: KpiService, SmallCellSuppression; E16: –; E17: read-only reporting role grants · V25; E18: none new; E19: –; E20: manager-workspace kpi.ts for new KPIs
E18 | E13: platform only; E15: ConfigService, StaffMemberRepository, ClinicSiteRepository; E16: business / site calendar, roster feed, maker-checker, flag register; E17: masterdata · V21; E18: none new; E19: –; E20: oh-workspace screens/admin/
E19 | E13: platform only; E15: ApiRateLimitFilter, DocumentService.generateSigned(…, DataClassification.RESTRICTED_CLINICAL), tools/security/security-verification.js, rbac-matrix.js; E16: startup guard against demo identities, programme attribute for restricted documents; E17: docs · V23; E18: guardrail tests (noStandardStreams style); E19: –; E20: ESLint rule against dangerouslySetInnerHTML in all four apps
E20 | E13: platform only; E15: JobRunGuard, OpenTelemetry / Micrometer, Helm chart, Terraform deploy/terraform/azure; E16: SLO rules as code, synthetic probes, Flyway lint (proposed deploy/observability/, tools/perf/); E17: none (expand / contract guideline applies to everyone); E18: –; E19: –; E20: –
E21 | E13: E13 screens; E03 / E09 content; E15: PdfRenderer (wellnessz.documents.font-path), ClinicalTextDetector, employee-app src/i18n/; E16: locale layer in three workspaces; Arabic shaping in PDFs; E17: masterdata (languages, translation register, preferred language) · V26; E18: –; E19: –; E20: all four apps
E22 | E13: E01, E02 (EVO: idempotent create), E07, E11 (wallet data); E15: NotificationChannel + Channel.PUSH, IdempotencyService, Employee.badgeId, NotificationTemplates / ContentRules; E16: push channel bean; (proposed kernel SPI StatusWalletContributor) implemented by E07 and E11; E17: field · V37; E18: fieldModuleUsesSpisOnly; E19: –; E20: employee-app (offline queue, NFC, push, wallet), oh-workspace (sync conflicts)
E23 | E13: E03, E04 (resource owners), E15; E15: FhirController, FhirConfig, Hl7v2Service, TerminologyService, CodeSystem, InboundService, AuditService; E16: (proposed FhirResourceContributor in com.wellnessz.integration.fhir) implemented by E03 / E04; E17: interop · V38; E18: interopHubDoesNotReadClinicalModules; E19: –; E20: oh-workspace (interfaces, subscriptions, replay), partner-portal (onboarding kit)
E24 | E13: E05 (wz-e05-fitness), E07 (wz-e07-surveillance); E15: FitnessClearanceGuard, ChartContributor, DocumentService, CrewCertificateRepository data via E07, outbox crew-rostering; E16: module SPI (proposed AuthoritySubmissionGateway) – default assisted submission; (proposed SignatureProvider in wz-documents); E17: aeromedical · V36; E18: aeromedicalBuildsOnFitnessAndSurveillanceOnly; E19: –; E20: oh-workspace (AME screens), manager-workspace (crew licensing status)
E25 | E13: kernel; E05 via restriction codes in master data (no Maven dependency); E15: CaseService / OpenCaseCommand, AppointmentBooking, DutyAssignmentRepository, ConsentService, InboundService, IdempotencyService; E16: –; E17: fatigue · V40; E18: fatigueModuleIsIndependent; E19: /workspace/fatigue (aggregate FRMS view); E20: employee-app (sleep self-screen, FRMS consent), oh-workspace (queue), manager-workspace (aggregates)
E26 | E13: E17; E15: Pseudonymizer (WZ_PSEUDONYM_KEY), KpiService, SmallCellSuppression, ConsentPurpose.RESEARCH_DEIDENTIFIED, outbox / CDC; E16: purpose-specific pseudonymisation (extends Pseudonymizer), KPI definitions as code; E17: dataplatform · V27; E18: dataPlatformReadsNoModuleClasses; E19: /workspace/insights; E20: manager-workspace (dashboards), oh-workspace (research requests)
E27 | E13: E26 (data), E06 (queue – EVO); E15: Pseudonymizer, AuditService, PolicyEngine; E16: (proposed kernel SPI EarlyInterventionSignalSource) implemented by E27, consumed by E06; E17: predictive · V55; E18: predictiveIsAdvisoryOnly; E19: –; E20: oh-workspace (signals in early-intervention queue, feedback)
E28 | E13: E03 (wz-e03-record); E15: AiDocumentationProvider (module SPI, activated by wellnessz.record.ai.provider), AiAssistantService, ConsentPurpose.AI_DOCUMENTATION, OcrProvider / TesseractOcrProvider (D14); E16: provider adapter implementing AiDocumentationProvider; E17: docassist · V35; E18: docAssistBuildsOnRecordOnly; E19: –; E20: oh-workspace (capture, side-by-side review)
E29 | E13: platform (wz-masterdata, wz-security org scope); E15: ConfigService, OrgUnitRepository, PartnerOrganisation, CurrentUser org scope, customisation.featureFlags Helm plumbing; E16: extension launcher in apps/wz-core-app (D22), flag register reads; E17: tenancy · V39; E18: tenancyIsNotUsedByProductModules; E19: /workspace/tenancy (subsidiary onboarding tracker); E20: all four apps (branding tokens)
E30 | E13: E26 (wz-e26-dataplatform), E14 (via SPI); E15: CapacityDemandSource (kernel, consumed by E14 CapacityService), SmallCellSuppression, DutyAssignmentRepository; E16: implements CapacityDemandSource; E17: readiness · V70; E18: readinessIsAggregateOnly; E19: /workspace/readiness; E20: manager-workspace (executive readiness), oh-workspace (clinic demand)
E31 | E13: E12 (wz-e12-promotion); E15: ConsentService, PartnerOrganisation, CurrentUser.partnerOrganisation() (bound clients, rule R12), IdempotencyService, SmallCellSuppression; E16: –; E17: marketplace · V71; E18: marketplaceSharesNoClinicalData; E19: /workspace/marketplace (spend and outcome, suppressed); E20: employee-app (catalogue), partner-portal (vendors), oh-workspace (recommend)
E · Platform prerequisites
Platform prerequisite | E13: Delivered by; E15: What the consumer needs; E16: Consumers (H = hard, S = soft, W = workbook); E17: Gate for
E15 broker adapter (D3) – production EventPublisher for Azure Service Bus or Kafka | E13: E15 (Q1–Q3); E15: Durable transport for outbox destinations, replay, dead letters; E16: E20 W (failover replays outbox), E23 H, E25 H, E26 H (CDC / broker feed); E17: Code: E26 pipeline, E23 subscriptions; go-live: all
E15 connectors (12, P1–P3) | E13: E15 + consumer adapters in E05, E06, E08, E10, E11, E12; E15: Real partner transports behind existing SPIs; E16: E05, E06, E08, E10, E11 (H, go-live), E12 S, E22 W (HRIS cache, push), E24 W (authority gateway transport), E31 W (benefits, vendors); E17: Go-live of delivered modules
E16 key wrapping / CMK (D5, SEC-E09) | E13: E16 + E19 SEC-E09; E15: KMS-wrapped data keys, re-encryption job, CMK on PostgreSQL before the PROD server and replica exist; E16: E20 H, E26 W (purpose keys), E27 W, E29 W (per-tenant keys for instance-per-tenant); E17: E20 code and PROD build
E16 consent, ABAC and audit (MFA enrolment, anchoring, SIEM export, purge jobs) | E13: E16; E15: Consent purposes, audit anchoring, purge of OH records (G10); E16: E21 W (guard vocabulary), E22 W, E23 W, E24 W (signature), E25 W, E28 W, E31 W; E17: Go-live (G10, G11)
E17 / E26 data layer | E13: E17 completion (H1) → E26; E15: De-identified view, KPI API, reporting role (O7), then CDC store, pseudonymisation, semantic layer, feature store; E16: E26 H on E17; E25 S, E27 H, E28 W (evaluation set), E30 H, E31 S on E26; E17: Code: E27, E30
E18 configuration (calendar O10, roster feed O9, maker-checker, flag register O34) | E13: E18; E15: Business calendar for SLAs and deadlines, governed flags, languages, terminology registry, content packs; E16: E20 W (flags), E21 S, E23 S, E24 W (deadline timers, AME designations), E29 H; E17: Code: E29; value: E21, E23
E19 security controls (admission, private control plane, MASVS, pen-test scope, extension signing) | E13: E19; E15: Signed-image admission (SEC-E03), private paths (SEC-E04), mobile hardening (SEC-E11), threat model per epic; E16: E20 H, E22 H, E29 H; E26 W (TRE), E28 W (provider assessment), E31 W (vendor due diligence); E17: Code: E22 release builds, E29 extension loader; go-live: all
E20 SRE (two-region, SLOs, load tests, flags governance, upgrade orchestration) | E13: E20; E15: Region pair for every in-country store; capacity model; canary; instances and upgrades; E16: Go-live H; E26 S (analytics store in the region pair); E27 W (monitoring); E29 H; E17: Go-live; E29 code
E13 app shell | E13: E13 completion; E15: Store-ready Capacitor shell, secure storage, MAM; E16: E22 H, E21 W, E25 W, E31 W; E17: Code: E22
E21 i18n | E13: E21; E15: Locale layer, Arabic shaping, translation register; E16: E28 S (Arabic transcripts), E25 W (instrument translations), E29 W (branding), E31 W; E17: Value
E23 hub | E13: E23; E15: FHIR profiles and document exchange; E16: E24 S (authorities with APIs); E17: Value
F · External prerequisites
ID | E13: External prerequisite; E15: Needed by; E16: Blocks; E17: Fallback that lets code be generated now; E18: Owner
X1 | E13: Partner APIs, sandboxes, test data and certificates: HRIS, rostering, EHS transport, toxicology LIMS, insurer / TPA, authority e-reporting, ERP, EAP, campaign app, wearable aggregator, public-health authority, SMS gateway; E15: E15 (all 12), E22 (HRIS cache), E23 (partner hospital, v2 laboratory), E25 (rostering), E31 (benefits); E16: Go-live; E17: Existing simulated defaults and outbox + content-free e-mail; E18: Integration lead, partner managers
X2 | E13: Terminology licences and national editions (SNOMED CT, ICD, LOINC – D10); E15: E23 (BL-009, BL-010); E16: Code of the terminology server integration; go-live; E17: Starter subset in TerminologyService; E18: Product owner, procurement
X3 | E13: Aviation-authority medical interface confirmation in writing (API, structured upload or portal only); E15: E24 (BL-001); E16: Code of the API client; go-live; E17: Assisted-submission package and receipt reconciliation (works for portal-only authorities); E18: AME lead
X4 | E13: Trust service provider for advanced / qualified signatures with in-country processing (D12); E15: E24 (BL-004, BL-005); later other externally effective documents; E16: Code of the signature adapter; E17: Current SHA-256 simple signature in DocumentService.sign; E18: Platform security, procurement
X5 | E13: MDM / MAM vendor and tenancy, store developer accounts with health-data declarations, push provider accounts under the client; E15: E13, E22 (BL-001–003, BL-008); E16: Release builds; push go-live; E17: In-memory token fallback in debug builds only; logging channel; E18: Client IT, T3
X6 | E13: In-country assistant hosting (locally hosted) or contracted provider with DPA, in-country processing, no retention, no training on WellnessZ data (D13); E15: E28 (BL-001, BL-003); E16: Code of the provider adapter beyond a stub; pilot; E17: No provider enabled (wellnessz.record.ai.provider: none); E18: CMO, DPO, CISO
X7 | E13: FRMS interface, consent model and minimal dataset agreed with the FRMS manager / vendor; E15: E25 (BL-002, BL-004); E16: Code of the inbound endpoint contract; E17: Manual referral through the existing self-referral path; E18: FRMS manager, T2
X8 | E13: National / emirate-level health information exchange eligibility and profile set; E15: E23 (BL-005, BL-011); E16: Code of the HIE connector (H3); E17: – (H3 item only); E18: Integration architect, Legal
X9 | E13: Benefits-system API and vendor DPAs, security due diligence; E15: E31 (BL-001, BL-003, BL-008); E16: Code of eligibility and hand-off; E17: Eligibility by subsidiary / role from HRIS master only; E18: HR benefits, Procurement, DPO
X10 | E13: Licensed instruments and validated translations (sleep screening, PHQ-9 / GAD-7 Arabic, destination content); E15: E21 (BL-010), E25 (BL-007); E16: Content go-live; E17: Instrument stored as configuration, status DRAFT; E18: Clinical governance
X11 | E13: Independent assessors: penetration test and retest (G1), WCAG 2.2 AA audit, MASVS assessment; E15: E19 (BL-001/-002, BL-030), E21 (BL-001), E22; E16: Go-live evidence; E17: –; E18: CISO, Head of Experience
G · Decision and sign-off prerequisites
ID | E13: Decision / sign-off; E15: Needed by; E16: Gates; E17: Reference
DS1 | E13: Clinical safety officer appointed (registered clinician with health-IT safety training); E15: E24, E25, E27, E28 (and E02, E05 evolution); E16: Code of any clinical-decision feature: hazard log entry before the story is ready; E17: Strategy 9.3, decision S6
DS2 | E13: AI governance board chartered (CMO, CSO, DPO, CISO, legal, employee representative); E15: E27 (BL-001), E28 (shared); E16: Any model or assistant code beyond spikes; E17: S6, E27-F01
DS3 | E13: DPIA per new processing: E22 offline dataset, E25 FRMS referral, E26 de-identification standard and TRE, E27 per use case, E28 assistant, E30 readiness model, E31 hand-off; DPIA screening for every other epic; E15: as listed; E16: Code that processes the new data category; E17: Developer Guide DoD #9, CI/CD 10.5 step 1
DS4 | E13: PMO numbering – E15 security epic renumbered E19, E20–E31 adopted as *Planned*; E15: All; E16: Module names, ticket prefixes, ModuleRegistry codes, Flyway file names; E17: Decision S2
DS5 | E13: Architecture decisions: D3 broker, D5 CMK / envelope encryption, D10 terminology, D12 signature level, D13 assistant provider, D14 OCR, D22 extension model, S8 tenancy direction, D4 mobile distribution; E15: E15, E16 / E19 / E20, E23, E24, E28, E28, E29, E29, E22; E16: The design of the adapter that implements the SPI; E17: Strategy Appendix B
DS6 | E13: Clinical / content sign-offs (CMO, MRO, Legal, DPO): CREW_FATIGUE red flags, authority templates and limitation codes, translated instruments, de-identification standard, retention classes (G10); E15: E25, E24, E21, E26, E16; E16: Content go-live (code can ship with DRAFT content); E17: Strategy 4.2, G9, G10
DS7 | E13: Employee-representative consultation and privacy-notice update; E15: E25 (BL-011), E27 (BL-011), E28; E16: Live use; E17: Strategy 6.4
DS8 | E13: Error-budget policy signed (release freeze rules); E15: E20 (BL-005); E16: Canary and release gating in Wave 2; E17: E20-F02
H · Environment prerequisites
ID | E13: Environment; E15: Needed by; E16: Gate
N1 | E13: Tier-0 two-region in-country Azure landing zone (GL-04, 16-week plan in the decision pack): primary + warm standby, allowed-locations policy, CMK, replicated registry, immutable backup vault; E15: E20 (builds it), PROD go-live (G7), every epic that stores data in PROD; E16: Go-live; recovery-region access request (UAE Central or equivalent) is the long lead item (SR5)
N2 | E13: In-country analytics store and landing / curated zones in the same region pair; E15: E26 (BL-001), E27, E30, E25 (indicators), E31 (ROI); E16: Code of the E26 pipeline needs at least a DEV store
N3 | E13: Production-like UAT with synthetic data at volume (50K staff, 30K crew rosters, 5 years of cases); E15: E20 (BL-006, BL-007), E19 pen test, E29 isolation suite; E16: Go-live evidence (G8)
N4 | E13: Device lab / test matrix and MDM test tenant; E15: E13, E22 (BL-012), E21 (assistive technology); E16: Release builds
N5 | E13: Trusted research environment (isolated workspace); E15: E26 (BL-011), E27 training; E16: E27 model code

## Build order (waves)
Build order – waves, critical paths, team allocation, entry and exit criteria
Six teams (H1) → five (H2) → four (H3) per the Capacity plan; team mergers are a proposal for the H1 / H2 gates
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Remaining Epics Build Plan, developer-facing ¦ 30 October 2026 ¦ effort indicative
Waves
Wave | Sprints (2 weeks) | Dates (indicative) | Increment | Funded teams | Epics in build | Goal | Demand / available team-sprints
0 – Readiness | Sprint 0 | 2 – 13 Nov 2026 | 6 (start) | 6 | Scaffolding for all; spikes | Numbering, catalogue entries, Flyway register, ArchUnit skeleton, DoR for Wave 1, external requests sent | part of Wave 1
1 – Go-live readiness (H1) | 1–12 | 16 Nov 2026 – 30 Apr 2027 | 6 | 6 | E13, E15, E16, E17, E18 (complete); E19 Now / Next; E20 H1; E22 H1; E21 H1; E26 H1; spikes E23, E24, E28 | Gates G1–G11, PROD live, P1 connectors live, KPI baselines started | 48.6 / 50.8 (Q2 alone 105 %)
2 – Scale foundations (H2a) | 13–25 | 3 May – 29 Oct 2027 | 7 | 5 | E15 tail; E19 Later; E20 H2; E21, E22 H2; E23; E24 build; E26 H2; E28 build; E25 and E29 start (Q4) | Offline field app, first FHIR / v2 interfaces, authority templates and signatures, data pipeline E01–E14, assistant in pilot build | 36.0 / 42.2
3 – Intelligence and regulators (H2b) | 26–38 | 1 Nov 2027 – 28 Apr 2028 | 8 | 5 | E21, E22 finish; E24, E26 finish; E23, E25, E28, E29 continue; E27 starts | First authority submission, semantic KPI layer, assistant pilot, tenancy factory, E27 silent pilot; H2 gate | 22.8 / 42.2
4 – Ecosystem (H3) | 39–77 | 1 May 2028 – 26 Oct 2029 | 9, 10, 11 | 4 | E23, E25, E28 finish (Q7–Q8); E27, E29 finish (Q10); E30, E31 | Live advisory signals, signed extensions, digital twin, marketplace; H3 review | 43.4 / 101.4
Critical paths
Path | Chain | Why it is critical | Float
CP1 – Tier-0 go-live | D5 decision → E16 CMK / envelope encryption (SEC-E09, E19-BL-021/-022) → E19 admission (SEC-E03) → E20-BL-001/-002/-003 two-region stack and scripted failover → E20-BL-006/-007 load test, E20-BL-010 first DR drill → GL-03 pen test and retest → go-live gate (29 Mar 2027) | CMK cannot be added to an existing PostgreSQL server; the recovery stack needs admission and keys first; the drill and the pen test are go-live conditions (G1, G7, G8) | None – any slip moves go-live
CP2 – connectors | D3 broker decision → E15 broker adapter → P1 connectors (HRIS, rostering, EHS, LIMS, insurer, authority, public-health) → E05 / E06 / E10 go-live | Three delivered modules are rated R until their connector is live; partner readiness is external (SR2) | Low; mitigated by decision S5 (integration uplift)
CP3 – data to intelligence | E17 completion → E26-BL-001/-002/-004 store, CDC, pseudonymisation → E26 semantic layer and feature store (BL-009, E27-BL-004) → E27 governance, safety case, silent pilot → E27 live → E30 | No model without a governed, pseudonymised platform; E30 needs both aggregates and forecasts | ≈ 1 quarter in H3
CP4 – regulator | E24-BL-001 authority formats + E24-BL-004 trust service provider (D12) → signature adapter → authority gateway → first submission (Q6) | External answers decide whether an API client is built at all (SR9) | ≈ 1 quarter
CP5 – governance | S6 → CSO + AI board → E28 DPIA and safety case → contract (X6) → provider adapter → 5-clinician pilot | Shared board also gates E27 | ≈ 1 quarter
Per-team demand per quarter (team-sprints; ≈ 4.2 available per team per quarter)
Team | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9–Q10 | Q11–Q12
T1 Clinical Care | 0 | 1.8 | 3.8 | 3.8 | 3.8 | 3.8 | 2.8 | 2 | 2 | 2
T2 Workforce Health | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 2.8 | 2.8 | 2.8
T3 Experience & Mobile | 2.8 | 3.8 | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0
T4 Integration | 7.3 | 8.3 | 8.3 | 1 | 1 | 1 | 1 | 1 | 0 | 0
T5 Platform & SRE | 9.7 | 9.7 | 3.7 | 4.6 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
T6 Data & Analytics | 2 | 3 | 1 | 1 | 1.8 | 1.8 | 1.6 | 1.6 | 1.6 | 0.8
Parallel work per team and wave
Wave | Team | Builds in parallel | Hands off / receives
1 (6 teams) | T1 Clinical Care | Sign-off support E01–E05, E08; E15 consumer adapters for E05 rostering transport and E08 ClaimsSubmissionGateway (with T4); spikes E24-BL-001, E24-BL-004; E28-BL-001 / -002 with the CSO | Receives E15 broker; gives authority answers to Wave 2
| T2 Workforce Health | E15 consumer adapters: E06 AbsenceFeedConnector, E10 LIMS bound client, E11 public-health submission (with T4); E25-BL-001 CREW_FATIGUE review; E21-BL-010 translation register content | Receives E15 broker and partner sandboxes
| T3 Experience & Mobile | E13 completion; E22-BL-001/-002/-003/-012 (secure storage, MAM, distribution, device matrix); E21-BL-001/-002/-004/-006/-007 | Gives store-ready shell to E22 Wave 2
| T4 Integration (+ S5 uplift) | E15 broker adapter (D3) and the 12 connectors; E23-BL-005 HIE spike, E23-BL-009 terminology licences | Gives broker to E26, E23, E25
| T5 Platform & SRE (+ champions) | E16, E18, E19 Now / Next, E20-BL-001…008, -010, -014, -015; Wave 0 scaffolding (TP-01…TP-04, TP-10) | Critical path CP1
| T6 Data & Analytics | E17 completion; E26-BL-001/-002/-004/-005/-006/-013 | Gives store and pseudonymisation to Wave 2
2 (5 teams) | T1 Clinical Care | E24 build (BL-002/-003/-005/-006/-007/-008/-009); E28 build (BL-003…-009); EVO share | Receives E18 calendar, X3 / X4 / X6 answers
| T2 + T3 → "Workforce Health & Experience" (proposal) | E22 H2 (offline sync, NFC, push, wallet); E21 H2 (locale layer, translation workflow, time zones); E25 start (BL-002/-003/-004) in Q4; EVO share | Offline sync needs TP-09 in E01 / E02
| T4 Integration | E15 tail (Q3); E23 (IG, Procedure / Consent / Task, conformance, subscriptions, v2, terminology server, MHD) | Gives transports to E24 gateway and E25 FRMS
| T5 Platform & SRE | E19 Later; E20 H2 (chaos, Flyway lint, canary, flags); E29 start Q4 (BL-001 tenancy analysis, BL-008 isolation suite, BL-009 flags) | Flag register shared with E18
| T6 Data & Analytics | E26 H2 (BL-003, -007…-012) | Gives feature store to E27
3 (5 teams) | T1 Clinical Care | E24 finish (first submission, BL-010/-011); E28 pilot (BL-010) and staged roll-out; EVO | –
| T2 + T3 | E21 / E22 finish (Q5); E25 (BL-005…-010); EVO | Indicators via E26
| T4 Integration | E23 (live hospital, v2 laboratory, partner kit BL-012); transports for E24 / E25 | –
| T5 Platform & SRE | E29 provisioning (BL-002…-005), flags read by features | –
| T6 Data & Analytics | E26 finish; E27-BL-001…-005, -010, -011 (governance, feature store, silent pilot) | H2 gate evidence
4 (4 teams, proposal) | A – Clinical & Workforce Health (T1 + T2 + experience engineers) | E25 finish (Q7), E28 finish (Q7), E31 (Q8–Q12), EVO | –
| B – Integration & Interoperability (T4) | E23 H3 (PIXm / PDQm, national exchange) to Q8; E31 eligibility and vendor imports; E30 roster / network feeds | From Q9 may merge into C if demand stays at 0
| C – Platform & SRE (T5) | E29 signed extensions, branding, upgrade orchestration, instance-per-tenant (to Q10); E20 run and drills | –
| D – Data & Analytics (T6) | E27 live pilot and monitoring (to Q10); E30 (Q7–Q12) | –
Entry and exit criteria per wave
Wave | Entry criteria | Exit criteria
0 | Strategy S1, S2, S3, S7 approved or on the steering agenda; six team leads named | E19–E31 codes in ModuleRegistry (disabled); Flyway reservation register live with V21 onwards; ArchUnit skeleton rules merged; docs/increment-06/ folder and e2e-increment6.js skeleton; external requests X1–X6 sent; DoR met for every Wave 1 story in Sprint 1
1 | Wave 0 exit; D3 and D5 decided by end of Sprint 2; Tier-0 decision pack approved | G1–G11 met; PROD live; P1 connectors live; E13, E16, E17, E18 at production grade; E19 Now done, Next ≥ 50 %; E20 first drill passed; E26 store + CDC E01–E08 + pseudonymisation in DEV / UAT; spikes E23-BL-005, E24-BL-001 / -004, E28-BL-001 / -002 decided; first monthly SLO report; e2e-increment6.js green
2 | H1 gate passed; funding for five teams (S10); CSO appointed and AI board chartered (S6); X2, X3, X4 answered | E15 complete (12 connectors); E19 G1–G6 and Later items closed; E20 chaos programme and two zero-downtime releases; E22 offline capture in field test; E23 IG published + v2 laboratory in UAT; E24 templates and signature adapter in UAT; E26 pipeline E01–E14 with quality rules; E28 adapter in UAT with DPIA approved; E25 and E29 decision records; e2e-increment7.js green
3 | Wave 2 exit; E27 DPIA and safety case approved; X6 contract signed | E21 WCAG audit clean; E22 live at airside posts; E24 first electronic submission with receipt; E26 every client KPI from the semantic layer; E28 5-clinician pilot report; E29 one subsidiary onboarded through the factory in ≤ 4 weeks; E27 silent-pilot report to the board; H2 gate (Strategy 4.3); e2e-increment8.js green
4 | H2 gate passed; funding for four teams; E27 board decision on live use | E23 live hospital + national exchange where permitted; E27 advisory signals live in pilot units with drift and fairness monitoring; E29 signed extension model and instance-per-tenant reference; E30 readiness dashboard and scenarios used in the outbreak exercise; E31 three vendors live under DPA; H3 review; e2e-increment9/10/11.js green

## Module scaffold blueprint
Module scaffold blueprint – one row per new epic
modules/wz-eNN-<name> · package com.wellnessz.eNN · one schema per module · Flyway next free from V21 (strict order) · E2E per increment 6–11
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Remaining Epics Build Plan, developer-facing ¦ 30 October 2026 ¦ effort indicative
Blueprint
Epic | Module | Package | Schema | First Flyway (indicative) | SPIs to implement | SPIs / services to consume | BFF resources | Web app | Roles (new = proposed) | E2E script | Docs to update
E19 | none – platform/wz-security, platform/wz-documents, CI, Terraform, Helm | existing | docs (column) | V23 __e19_restricted_document_programme.sql | startup guard (proposed DemoIdentityGuard) | ApiRateLimitFilter, DocumentService, AuditService | none | all four (ESLint rule) | – | tools/security/security-verification.js + e2e-increment6.js | rename docs/security/epics/E15-* to E19 (PMO); doc 02; Security Enhancement Guideline; CI/CD Guide (new workflow)
E20 | none – deploy/terraform/azure, deploy/helm/wellnessz, .github/workflows, deploy/observability/ and tools/perf/ (proposed folders) | – | – | none (owns the expand / contract lint) | – | JobRunGuard, OpenTelemetry metrics | none | none | – | drill report + e2e-increment6.js smoke against both regions | Deployment Architecture, CI/CD Guide 8 and 9, runbooks
E21 | none – four web apps, platform/wz-documents (PdfRenderer), platform/wz-common (ClinicalTextDetector), platform/wz-masterdata | existing | masterdata (tables) | V26 __e21_languages_translation_register.sql | – | PdfRenderer, ClinicalTextDetector, ConfigService | none | all four (locale layer) | – | e2e-increment6.js (employee Arabic) and e2e-increment7.js (workspaces, axe checks) | Developer Guide 10, app READMEs, accessibility statements
E22 | modules/wz-e22-field | com.wellnessz.e22 | field | V37 __e22_field.sql | NotificationChannel (Channel.PUSH); proposed kernel SPI StatusWalletContributor (implemented by E07, E11) | IdempotencyService, NotificationTemplates, ContentRules, Employee.badgeId, AuditService | none (/api/v1/field/** proxied) | employee-app (offline queue, NFC, push, wallet), oh-workspace (sync conflicts) | – (uses FIRST_AIDER, CLINIC_RECEPTION) | e2e-increment7.js (offline emulation) | Developer Guide 10.1 (MDM keys), setup guide (push, MDM)
E23 | modules/wz-e23-interop (+ platform/wz-integration fhir, hl7, terminology) | com.wellnessz.e23 | interop | V38 __e23_interop.sql | proposed FhirResourceContributor (implemented by E03, E04) | FhirController, Hl7v2Service, TerminologyService, InboundService, IdempotencyService, ConsentService, ConnectorRegistry | none | oh-workspace (interfaces, replay), partner-portal (onboarding kit) | INTERFACE_ANALYST (new, internal) | e2e-increment7.js | FHIR IG (new docs/interop/), API contract, doc 01 integration section
E24 | modules/wz-e24-aeromedical | com.wellnessz.e24 | aeromedical | V36 __e24_aeromedical.sql | FitnessClearanceGuard (certification guard), ChartContributor; module SPI proposed AuthoritySubmissionGateway (default: assisted submission + outbox); proposed SignatureProvider in wz-documents | DocumentService, AuditService, outbox crew-rostering, JobRunGuard (deadline timers), E18 calendar | none | oh-workspace (AME), manager-workspace (crew licensing status) | – (uses AME, CREW_LICENSING) | e2e-increment7.js | API contract, solution design, Customisation Guide 7.2 (new seam)
E25 | modules/wz-e25-fatigue | com.wellnessz.e25 | fatigue | V40 __e25_fatigue.sql | – | CaseService (CaseSource.FRMS_REFERRAL, proposed), AppointmentBooking, DutyAssignmentRepository, ConsentService (FRMS_REFERRAL, proposed), InboundService, IdempotencyService, SmallCellSuppression | /workspace/fatigue | employee-app, oh-workspace, manager-workspace | FRMS_MANAGER (new, aggregate only) | e2e-increment7.js (start) / e2e-increment8.js | API contract, consent wording, triage protocol notes
E26 | modules/wz-e26-dataplatform (+ platform/wz-analytics, pipeline in deploy/) | com.wellnessz.e26 | dataplatform | V27 __e26_dataplatform.sql | – | Pseudonymizer (purpose keys), KpiService, SmallCellSuppression, ConsentService | /workspace/insights | manager-workspace (dashboards), oh-workspace (research requests) | DATA_STEWARD, RESEARCHER (new) | e2e-increment6.js (KPIs) / e2e-increment7.js | Data catalogue, de-identification standard, doc 02
E27 | modules/wz-e27-predictive | com.wellnessz.e27 | predictive | V55 __e27_predictive.sql | proposed kernel SPI EarlyInterventionSignalSource (consumed by E06 – EVO change) | Pseudonymizer, PolicyEngine, AuditService | none | oh-workspace (early-intervention queue) | – | e2e-increment8.js (silent: no UI) / e2e-increment9.js | Model cards, safety case, privacy notice
E28 | modules/wz-e28-docassist | com.wellnessz.e28 | docassist | V35 __e28_docassist.sql | AiDocumentationProvider (E03 module SPI; activated by wellnessz.record.ai.provider) | AiAssistantService, ConsentService (AI_DOCUMENTATION), AuditService, OcrProvider (D14) | none | oh-workspace (capture, side-by-side review) | – | e2e-increment7.js (stub provider) | DPIA, safety case, DPO monthly report, API contract
E29 | modules/wz-e29-tenancy (+ launcher in apps/wz-core-app, flag register in wz-masterdata) | com.wellnessz.e29 | tenancy | V39 __e29_tenancy.sql | extension loader (D22) | ConfigService, OrgUnitRepository, PartnerOrganisation, customisation.featureFlags | /workspace/tenancy | all four (branding tokens), oh-workspace (onboarding tracker) | TENANT_ADMIN (new) | e2e-increment8.js | Client Customisation Guide 5, 7, 9 (extensions replace forks), CI/CD 10.6
E30 | modules/wz-e30-readiness | com.wellnessz.e30 | readiness | V70 __e30_readiness.sql | CapacityDemandSource (consumed by E14 CapacityService) | E26 semantic layer, SmallCellSuppression, DutyAssignmentRepository | /workspace/readiness | manager-workspace (executive), oh-workspace (clinic demand) | WORKFORCE_PLANNER (new, aggregate only) | e2e-increment9.js | Scenario assumptions register, DPIA
E31 | modules/wz-e31-marketplace | com.wellnessz.e31 | marketplace | V71 __e31_marketplace.sql | – | ConsentService (MARKETPLACE_HANDOFF, proposed), PartnerOrganisation + bound clients (R12), IdempotencyService, SmallCellSuppression | /workspace/marketplace | employee-app (catalogue), partner-portal (vendors), oh-workspace (recommend) | – (vendors use PARTNER_PROVIDER with MFA) | e2e-increment9.js | Vendor onboarding runbook, DPA register
Numbering conventions
Item | Convention | Example
Maven module | modules/wz-eNN-<name> | modules/wz-e24-aeromedical
Package | com.wellnessz.eNN (since increment 3) | com.wellnessz.e24
Registration | ENNModule implements CaseModule, code ENN, flag modules.eNN.enabled (seed false in the first migration) | E24Module
Schema | one schema per module, lower case, no prefix | aeromedical
Flyway | V<n>__eNN_<purpose>.sql in apps/wz-core-app/src/main/resources/db/migration; next free is V21; strict order (no outOfOrder) – a reserved number that misses its merge window is renumbered to the next free one | V36__e24_aeromedical.sql
Wave blocks (indicative) | Wave 1: V21–V34 · Wave 2: V35–V54 · Wave 3: V55–V69 · Wave 4: V70 onwards; within a wave, numbers are taken in merge order | –
Demo data | apps/wz-core-app/src/main/resources/db/demo/R__demo_eNN_<name>.sql | R__demo_e24_aeromedical.sql
Integration test | IncrementNxxxIntegrationTest in apps/wz-core-app/src/test/java/com/wellnessz/app/ | Increment7AeromedicalIntegrationTest
E2E | tools/e2e/e2e-incrementN.js, screenshots docs/images/screens/increment-NN/ | e2e-increment7.js
Docs | docs/increment-NN/ (solution design, RTM, release notes, API contract) | docs/increment-07/
Proposed new SPIs (not in the code base yet)
Item | Kind | Where (proposed) | Implemented by | Consumed by | Default when absent
StatusWalletContributor | kernel SPI | com.wellnessz.casekernel.support | E07 (certificates), E11 (travel vaccinations) | E22 wallet | Empty wallet card
EarlyInterventionSignalSource | kernel SPI | com.wellnessz.casekernel.support | E27 | E06 early-intervention queue | Rule-based triggers only (today)
FhirResourceContributor | platform SPI | com.wellnessz.integration.fhir | E03, E04 | E23 IG export and subscriptions | Today's FHIR mappings
AuthoritySubmissionGateway | module SPI (E24) | com.wellnessz.e24 | E24 default; API clients per authority | E24 submission service | Assisted submission + outbox
SignatureProvider | platform SPI | com.wellnessz.documents | default simple signature; TSP adapter (D12) | DocumentService.sign, E24 | SHA-256 simple signature (today)
KeyWrappingProvider | platform SPI | com.wellnessz.secrets | KMS adapters (Azure Key Vault, Cloud KMS) | FieldEncryptor / MasterKey | Local master key (today)
Overlaps to resolve before code is generated
Overlap | Epics | Resolution
Per-user channel preferences | E13 completion and E22-F04 / BL-009 | Build once in E13 (Wave 1); E22 adds the push channel
Feature-flag governance | E18 (O34), E20-BL-013, E29-BL-009 | One flag register in wz-masterdata; E20 adds owner, expiry and audit; E29 adds tenant scope
Pseudonymisation keys | E16 (keys), E26-BL-004 (purpose keys), Pseudonymizer | E26 owns purpose keys, E16 owns key wrapping and rotation
Electronic signature | E16 identity, E24-F02, D12 | SignatureProvider in wz-documents; E24 delivers the first adapter
Readiness / capacity forecasts | E27-F06, E30-F02 | E27 publishes forecasts to E26; E30 consumes and feeds E14 through CapacityDemandSource
Step by step – scaffolding a new epic module (E24 example)
# | Step | What to do | Proof
1 | Ticket and design | E24-BL-00x, classification, disclosure levels, DPIA screening, threat-model delta, hazard log (CSO) | DoR met
2 | Branch | feature/E24-BL-002-authority-templates from main | ruleset
3 | Maven module | modules/wz-e24-aeromedical/pom.xml from the Developer Guide 2.2 template; dependencies wz-case-kernel, wz-security, wz-integration, wz-masterdata, wz-documents, wz-e05-fitness, wz-e07-surveillance; <module> and <dependencyManagement> in the root pom.xml; dependency in apps/wz-core-app/pom.xml; /modules/wz-e24-aeromedical/ in .github/CODEOWNERS | ./mvnw verify
4 | Registration | com.wellnessz.e24.E24Module implements CaseModule (code E24); catalogue entry already added in Wave 0; ModuleRegistry.requireEnabled("E24") on every use case and job; listeners check isEnabled and skip | GET /api/v1/modules shows IMPLEMENTED
5 | Migration | Take the next free number (indicative V36__e24_aeromedical.sql): create schema aeromedical, tables, encrypted columns as text, explicit grants to ${app_role}, seed modules.e24.enabled = false; add aeromedical to the five schema places (TP-02) | integration tests on a fresh database
6 | Security | @PreAuthorize per endpoint; AccessPolicy beans; status-only projection for crew licensing and rostering; EncryptedStringConverter on free text; audit actions AME_EXAM_*; content-free notification templates checked by NotificationRulesTest | unit + negative integration tests
7 | SPIs | Implement FitnessClearanceGuard (certification guard) and ChartContributor; define AuthoritySubmissionGateway with a default bean (assisted submission package + outbox), consumers inject ObjectProvider; signature through the proposed SignatureProvider with today's simple signature as default | ArchitectureTest
8 | ArchUnit | Add com.wellnessz.e24.. to the four package-list rules and aeromedicalBuildsOnFitnessAndSurveillanceOnly | ArchitectureTest
9 | Tests | Increment7AeromedicalIntegrationTest on IntegrationTestBase with the eight mandatory cases (Developer Guide 9.2); rule unit tests | ./mvnw verify
10 | Roles and realm | Reuse AME, CREW_LICENSING; update realm JSON and scope mappings only if roles change | E2E login
11 | BFF | Only if a /api/v1/workspace/... path is added: CORE_WORKSPACE_RESOURCES + ApiProxyPathTest | ./mvnw verify
12 | Web | oh-workspace screens in src/screens/, role routing in src/auth/roles.ts; manager-workspace whitelist in src/api/statusOnly.ts; Vitest | CI Web <app>
13 | E2E | Add the E24 section to tools/e2e/e2e-increment7.js; screenshots in docs/images/screens/increment-07/ | all E2E scripts green on a fresh database
14 | OpenAPI | curl -s http://localhost:8080/v3/api-docs ¦ jq . > docs/api/openapi.json; review the diff | PR review
15 | Docs | docs/increment-07/ (solution design, RTM, release notes, API contract), doc 01 module table, doc 02, Developer Guide new section, CI/CD Guide schema and role lists | docs Code Owners
16 | Flag and release | Ship dark (modules.e24.enabled=false and, where needed, WZ_FEATURE_E24_* read by the feature); vX.Y.0-rc.N → UAT → PROD | environment approvals

## Definition of ready
Definition of ready to generate code
Common criteria for every story, then epic-specific items; tick 'Met' per sprint (dropdown)
Airline Group Occupational Health Case Management (OHCM) ¦ v1.0 – Remaining Epics Build Plan, developer-facing ¦ 30 October 2026 ¦ effort indicative
Common definition of ready (every story)
# | Criterion | Evidence | Met?
DoR-01 | Epic number confirmed by the PMO (E19 renumbering, E20–E31 adopted) and the workbook *Decision* column reviewed for the HLR and feature | Workbook, ticket prefix E2x-BL-nnn
DoR-02 | Story ≤ 13 SP, acceptance criteria testable, traced to HLR and feature | Ticket
DoR-03 | Hard predecessors at the exit state named in the matrix (Section 3.6); soft ones assessed | Matrix row
DoR-04 | Data classification per table / column; restricted-class answer (E09 / E10 data excluded unless OH governance approves); disclosure levels and status-only projection defined | Design note
DoR-05 | DPIA screening done; retention class named; threat-model delta written by the security champion | Doc 02 entry
DoR-06 | External dependency either available in a sandbox or the simulated default agreed (◐ items) | Matrix row
DoR-07 | Module, package, schema and Flyway number reserved in the register (Section 6.1) | PR title V<n> reservation
DoR-08 | ArchUnit rule drafted (which packages the new code may and may not use) | Rule text in the design note
DoR-09 | Kernel / module SPI identified – existing (verified) or proposed with its default behaviour | Design note
DoR-10 | Roles, BFF path family and web app identified; new roles listed for the realm | Design note
DoR-11 | E2E check named in the increment script; screenshot names planned | Test plan
DoR-12 | For clinical-decision features: hazard-log entry by the clinical safety officer; for AI features: AI board approval of the use case | Hazard log, board minutes
Epic-specific readiness items
Epic | Ready to generate code when … | Owner | Met?
E13 | D4 mobile distribution decided; secure-storage plug-in and MAM SDK selected at exact versions; status-only field lists for crew scheduling and hygiene manager approved by the DPO
E15 | D3 broker decided; per connector: partner sandbox or recorded contract, mapping spec, DPO-approved outbound fields, bound machine client (CurrentUser.partnerOrganisation())
E16 | D5 ADR approved (E19-BL-021); key hierarchy and rotation runbook drafted; DPO retention classes for purge (purge code may ship disabled until G10)
E17 | KPI definitions signed by owners (RTW within 5 days, matched duty, documentation time, litigated-claim trend); reporting-role scope approved
E18 | Calendar data source and site list agreed; maker-checker roles agreed; flag-register design agreed jointly with E20 and E29
E19 | Pen-test window and rules of engagement; admission technology chosen (E19-BL-005); restricted-document programme attribute agreed with OH (E19-BL-010)
E20 | Tier-0 decision pack approved (S3); recovery-region access confirmed in writing (SR5); E16 CMK and E19 admission ready for PROD; synthetic dataset specification for 50K staff
E21 | WCAG auditor contracted; language list from HRIS data; Arabic font licence for PDFs; translation workflow chosen; validated instrument translations licensed
E22 | E13 store-ready; MDM / MAM tenancy and push accounts (X5); offline minimal dataset and maximum offline age approved by CMO and DPO; TP-09 (idempotent E01 / E02 creates) scheduled; MASVS scope agreed with E19
E23 | Terminology licences procured (X2); partner hospital and v2 laboratory sandboxes; IG publishing approach; FhirResourceContributor contract reviewed by T1 for E03 / E04
E24 | Authority formats and interface options confirmed in writing (E24-BL-001); trust service provider selected (D12); CSO hazard log for certification states; AME lead owns the template sign-off
E25 | FRMS interface, consent model and minimal dataset agreed (E25-BL-002); employee representatives consulted on the non-punitive principle; CREW_FATIGUE red flags signed; sleep instrument licensed
E26 | E17 complete; E15 CDC / broker in DEV; analytics store in the region pair (N2); de-identification standard approved by the DPO (E26-BL-005); purpose-key design agreed with E16
E27 | CSO appointed and AI board chartered; DPIA, safety case and regulatory classification for the use case; E26 feature store and pseudonymisation live; silent-pilot protocol and fairness threshold agreed
E28 | D13 spike decided; DPIA and safety case approved; DPA with in-country processing, no retention and no training; restricted classes excluded by default
E29 | S8 tenancy direction and E29 decision record; D22 extension design with signing (E29-BL-005); threat model and pen-test scope updated (E19); E20 upgrade orchestration available for instances
E30 | E26 aggregates live; E27 forecasts available or a baseline forecast accepted; E14 capacity model stable; DPIA for the readiness model
E31 | Vendor due-diligence checklist and DPA template (E31-BL-001); benefits-system API or HRIS-only eligibility agreed; consent wording for the hand-off; OH content-review process